## ReadMeFirst
INFO 8440 Team and Individual Project Plan, Time, Effort, Status Reporting Workbook
*** This is a sample, and a template ****
*** Teams submitting a RACI workbook that is not based on this Template will receive, at best, an Adequate rating ***
Created by: | Bill Nixon |  | Version | 5
History Table:
| Date | Version | Comments
| 2017-08-01 | 1 | Created and published
| 2019-10-17 | 2 | Added Actual RACI Columns, and Task Types
| 2018-12-01 | 3 | Added Person Sheets, and Daily Report
| 2021-01-21 | 4 | Created RACI Deliverables, and RACI Tasks sheets
| 2022-12-21 | 5 | Renamed sheets. Added more documentation and guidance.
Sheets
ReadMeFirst | This sheet. Gives an overview of the entire workbook
RACI Deliverables | Required. The latest version of the RACI Deliverables for the team for this project. This sheet is cloned at the first of every class day, and then updated.
RACI Tasks | Optional. The latest version of the RACI Tasks for the team for this project. This sheet is cloned at the first of every class day, and then updated.
Dlvrbls Day 3-1 | Required. The RACI Deliverables sheet as of Week 3 Day 1 at start of class. This should never be changed. Comparing this to the latest sheet will show the RACI changes, and thus team decisions.
By the time that the project is finished, there must be one backup sheet for each of all but the last 2 days (Briefing/Presentation Days) of the Project
Tasks Day 3-1 | Optional. The RACI Tasks sheet as of Week 3 Day 1 at start of class. This should never be changed.
Person1 | The Daily Time log for Person1 of the Team. Always insert new lines at the base of the list, so that the message at the bottom (Row 47 in the sampe) always stays.
** More Daily Log sheets needed - one for each team member! ** These should be kept in separate workbooks during the project, and submitted separately for final submission **
Gantt | Reserved Sheet for a Ecel based Gantt of the RACI Deliverables Sheet.
For the PM Docs version of this workbook, the Gantt will have no data, and thus no date range graphics, but it will have Excel formulas to create the graphics.
Guidance:
1) | Update RACI data only in the RACI sheet!
2) | The Activity Numbers in the Person Sheets are the code number for the Activity from the RACI
3) | All Required Deliverables for the Final Project submission must be provided in the Delvierables sheets. RFI and PM Docs Deliverable are optional.
4) | Every Deliverable Item must have a Responsible and Accountable person. It is allowable to be A,R, but someone else should do a Quality Check on all person's work.
5) | Formatting is left to you to do. This workbook is given to you as a guide. It must look different than this sample when submitted as INFO 8440 work.
6) | Save your work often. Save different versions of this file as backups.
7) | All dates must be formatted as DD-MMM or DD-MMM-YY 11-Jan-17 or 11-Jan
8) | The RACI-Actual Columns should only be filled in when the Actual differs from the Plan.
9) | Vlookup is used to echo the names of the deliverables into the Tasks sheets and the Gantt sheet
10) | Sheets are created to support filtering, not grouped reporting
11) | The Actual IsBuilt Date in RACI Deliverables indicates the date when the original creator has received a Quality OK rating from the team.
Usually, the component is then included in the final report and/or presentation
12) | In the RACI Deliverables and RACI Tasks sheets, from Row 7 and down, THERE MUST BE NO MERGED CELLS!
13) | Projected Effort data in the RACI+ Deliverables is expected in the Phase 3 Project, but optional in Phase 1
14) | The Deliverable Grouping is optional data.
15) | Minutes of Team Meetings are not required in this course. Instead, this RACI must be kept up to date, and backup sheets done every class day.
16) | This RACI+ workbook will be required as a weekly submission for later weeks in each project. Professor will provide details at that time.

## RACI Deliverables
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2022-01-28
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak | Anusha Asokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya keesari
Deliverable Group |  | DlvID | Project Final Deliverables (RFIs and PM Docs Deliverables are optional) | Need / Requirement ID | MayurKum Plan | Prajwal Plan | Anusha A Plan | Jigeesha Plan | Cathleen Plan | Chaitanya keesari | Professor's Marking Item ID# | Start Date | Due Date (M/D/Y) | Actual Effort Days | Actual Start Date (M/D/Y) | Actual IsBuilt Date (M/D/Y) | Done On Date (M/D/Y)
GA | Building | A | Letter of Transmittal | 20 | R |  | A |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | B | Cover Page | 20 |  |  | R | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | C | Page Headers, Footers and Numbering | 20 | A | R | [5 empty] | 2022-01-27 | 2022-01-28 | 1
GA | Building | D | TOC | 20 |  |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | E | Document History | 20 |  |  |  |  | R | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | F | Executive Summary | 21 |  |  | R |  |  | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | G | Assumptions | 21 | R |  |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | H | Conclusions | 21 |  | R |  |  |  | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | I | Background and overview of client | 22 | A |  | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | J | Requests for Information with NDA (included as an Appendix) | 22 |  |  | A | R |  |  |  | 2022-01-20 | 2022-01-21 | 1
GA | Building | K | Project Scope Document | 24 | A | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | L | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Need7 | R | A | [5 empty] | 2022-02-03 | 2022-02-07 | 4
GA | Building | M | AS-IS principles of OHT and/or Executive Decision Making operations | Need7 |  |  | R |  | A |  |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | N | To-Be persons / roles / actors and interactions of Executive Decision Making operations | 43 |  |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | O | Executive Dashboard annotated list of elements for the dashboard, | Need6 | R |  |  |  | A |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | P | Possible Future Analysis and Development for Executive Decision Making Process | 43 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | Q | Measuring Success and Failure in Changing the Executive Decision Making Process | 44 |  | A |  |  | R |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | R | Probable Benefits of Changing the Executive Decision Making Process | 46 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | S | Detailed References | 23 |  |  | R | A |  |  |  | 2022-02-10 | 2022-02-17 | 7
GA | Building | T | Business Challenges | 26 | R |  | A |  |  |  |  | 2022-02-03 | 2022-02-10 | 7
GA | Building | U | Current Brands Involved and their Statuses | 26 |  |  |  |  | A | R |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | V | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | 26 |  |  |  | R |  | A |  | 2022-02-04 | 2022-02-10 | 6
GA | Building | W | Known Client Requirements | 41 |  | R |  |  | A |  |  | 2022-01-29 | 2022-02-06 | 8
GA | Building | X | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | 45 |  |  | R | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Y | Gantt Chart |  | A | R |  |  | R |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Z | Persona For Executive Dashbaord |  |  | A |  |  | R |  |  | 2022-02-15 | 2022-02-17 | 2
GA | Building | AA | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Need22 |  |  |  | A |  | R |  | 2022-02-04 | 2022-02-07 | 3
GA | Building | AB | Gap Analysis Document | Need7 |  |  | A |  | R |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AC | Guidance on Using the Dashboard - Video or Text+Graphics | Need7 |  | R |  |  | A |  |  | 2022-02-08 | 2022-02-11 | 3
GA | Building | AD | TrackR Data Gen metric Data Sources List and DB Schema | Need7 | R | [6 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | AE | TrackR Data Gen metric Data Sources Data Overview / Profile | Need7 |  | R |  | A |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AF | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Need8 |  | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | AG | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Need8 |  | A |  |  |  | R |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AH | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Need8 |  |  | A | R |  |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AI | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Need8 |  |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AJ | ERD Diagram | 49 | R | A | [5 empty] | 2022-02-04 | 2022-02-08 | 4
GA | Building | AK | Pseudo-code Document | Need6 |  |  |  | A |  | R |  | 2022-02-10 | 2022-02-12 | 2
GA | Building | AL | Agile Development Document | 51 |  |  | R |  | A |  |  | 2022-02-06 | 2022-02-09 | 3
GA | Building | AM | Cockburn templates for all identified interactions | Need22 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | AN | List, References and General Details of Suggested Metrics | Need1 |  | R |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AO | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Need1 | R |  |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AP | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Need1 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AQ | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AR | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | R |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AS | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Need1 |  | R |  |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AT | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | A | R |  |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AU | Interview and/or survey of 6 OHT CPs | Need 2 | R | R | A |  |  |  |  | 2022-02-01 | 2022-02-03 | 2
GA | Building | AV | Data Listing of 6 OHT VPs Measurements of Business Success | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AW | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Need 2 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AX | Data Listing of 6 OHT VPs visions for a better managed OHT | Need 2 |  |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AY | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AZ | Interview and/or survey of 6 OHT VPs | Need 3 |  | A |  |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BA | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Need 3 |  |  |  | R | A |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BB | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Need 3 |  |  |  | A |  | R |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BC | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Need 3 |  | R |  |  |  | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BD | Listing of 6 OHT VPs Preferred learning style | Need 3 |  |  | R | A |  |  |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BE | Listing of 6 OHT VPs Preferred ways to implement new concepts | Need 3 |  |  |  |  | R | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BF | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Need 4 |  |  | R |  |  | A |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BG | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Need 4 |  |  |  | R | A |  |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BH | VP's Written Briefing on Executive and Analytical Dashboards | Need 4 | R | A | [5 empty] | 2022-02-03 | 2022-02-06 | 3
GA | Building | BI | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | R |  |  |  | A |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BJ | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | R |  |  | A |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BK | suggested VP training plans | Need 5 | R |  |  |  | A |  |  | 2022-02-11 | 2022-02-15 | 4
GA | Building | BL | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  |  | A |  | R |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BM | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BN | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | A | R |  |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BO | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | A |  |  | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BP | General configuration of Executive Dashboard using PowerBI | Need 6 |  | R | A |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BQ | Executive Dashboard Metric 1 using TrackR Data Generator Data | Need 6 | R | R | A |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BR | Executive Dashboard Metric 2 using TrackR Data Generator Data | Need 6 | A | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | BS | Executive Dashboard Metric 3 using TrackR Data Generator Data | Need 6 |  | R |  |  | A |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BT | Executive Dashboard Metric 4 | Need 6 | A | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | BU | Executive Dashboard Metric 5 | Need 6 |  | R |  | A |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BV | Executive Dashboard Metric 6 | Need 6 |  | R |  |  |  | A |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BW | Executive Dashboard menu / system map | Need 6 |  |  |  | A | R |  |  | 2022-02-07 | 2022-02-12 | 5
GF | Closing | BX | Merged Final Report |  | A | A | A |  | R |  |  | 2022-02-15 | 2022-02-17 | 2
GF | Closing | BY | Powerpoint Presentation |  |  | A |  | R |  |  |  | 2022-02-13 | 2022-02-17 | 4
GF | Closing | BZ | Final RFI report |  |  | A | R |  | R |  |  | 2022-01-28 | 2022-02-17 | 20
GF | Closing | CA | RACI+, Documentation, Backup Sheets |  |  | R |  |  | A |  |  | 2022-01-28 | 2022-02-18 | 21
GF | Closing | CB | Time and Effort Reporting |  | R | R | R | R | R | R |  | 2022-01-28 | 2022-02-17 | 20
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
|  |  |  | R | 14 | 21 | 16 | 14 | 13 | 12
|  |  |  | A | 13 | 12 | 13 | 14 | 16 | 13
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## RACI Tasks
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2020-09-17 | 3 | 2
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari | [9 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari
DlvID | TaskID | Project Final Deliverables (No Verb Words at the start) | Activity / Task (VERB: Subject) | Project Phase (see WBS) | MayurKumar | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany | Start Date | Due Date (M/D/Y) | Actual Effort (Days) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | 1.1 | Letter of Transmittal | Develop a cover page | Create | R |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.5 |  |  | 2022-02-09 | 2022-02-09
A | 1.2 | Letter of Transmittal | Develop a cover page | Pack and publish | R |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 1 |  |  | 2022-02-09 | 2022-02-09
B | 2.1 | Cover Page | Develop a cover letter | Create |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.16667 |  |  | 2022-01-28 | 2022-01-28 | R | C | C
B | 2.2 | Cover Page | Develop a cover letter | Pack and publish |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.16667 |  |  | 2022-01-28 | 2022-01-28
C | 3.1 | Page Headers, Footers and Numbering | Develop a header, footer and numbering | Create | A | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 1.5833 |  |  | 2022-01-27 | 2022-01-28
C | 3.2 | Page Headers, Footers and Numbering | Develop header, footer and numbering | Pack and publish | A | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 1.9167 |  |  | 2022-01-27 | 2022-01-28
D | 4.1 | TOC | Create a table of content | Publish |  |  |  | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.25 |  |  | 2022-01-27 | 2022-01-27
E | 5.1 | Document History | Research about documnent history document | Research |  |  |  |  | R | A | 2022-01-27 | 2022-01-28 | 1 | 0.5 |  |  | 2022-01-10 | 2022-01-18
E | 5.2 | Document History | Develop document history document | Create |  |  |  |  | R | A | 2022-01-27 | 2022-01-28 | 1 | 0.5 |  |  | 2022-01-10 | 2022-01-18
E | 5.3 | Document History | Publish document history document | Publish |  |  |  |  | R | A | 2022-01-27 | 2022-01-28 | 1 | 1 |  |  | 2022-01-10 | 2022-01-18
F | 6.1 | Executive Summary | Write summary for executives | Create |  |  | R |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 1 |  |  | 2022-01-20 | 2022-01-20
F | 6.2 | Executive Summary | publish summary for executive summary | Publish |  |  | R |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 0.5 |  |  | 2022-01-21 | 2022-01-21
G | 7.1 | Assumptions | Gather assumptions | Research | R |  |  | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.33333 |  |  | 2022-02-09 | 2022-02-09
G | 7.2 | Assumptions | Create asuumptions | Create | R |  |  | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.41667 |  |  | 2022-02-09 | 2022-02-10
G | 7.3 | Assumptions | Publish assumptions | Pack and publish | R |  |  | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.16667 |  |  | 2022-02-10 | 2022-02-10
H | 8.1 | Conclusions | Create conclusion | Create |  | R |  |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 0.25 |  |  | 2022-01-27 | 2022-01-28
H | 8.2 | Conclusions | Publish conclusion | Publish |  | R |  |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 0.91667 |  |  | 2022-01-27 | 2022-01-28
I | 9.1 | Background and overview of client | Develop document | Create | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 2.5 |  |  | 2022-01-27 | 2022-01-27
I | 9.2 | Background and overview of client | Publish final document | Publish | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 1.5 |  |  | 2022-01-28 | 2022-01-28
J | 10.1 | Requests for Information with NDA (included as an Appendix) | Create RFI Document | Create |  |  | A | R |  |  | 2022-01-20 | 2022-01-21 | 1 | 5.5833 |  |  | 2022-01-20 | 2022-01-20
J | 10.2 | Requests for Information with NDA (included as an Appendix) | Look out for questions need to ask | Research |  |  | A | R |  |  | 2022-01-20 | 2022-01-21 | 1 | 5.9167 |  |  | 2022-01-20 | 2022-01-20
J | 10.3 | Requests for Information with NDA (included as an Appendix) | Prepare Final RFI Document | Pack and publish |  |  | A | R |  |  | 2022-01-20 | 2022-01-21 | 1 | 6 |  |  | 2022-01-21 | 2022-01-21
K | 11.1 | Project Scope Document | Creating Document | Create | A | A |  | R |  |  | 2022-01-27 | 2022-01-28 | 1 | 1 |  |  | 2022-01-23 | 2022-01-23
K | 11.2 | Project Scope Document | Develop content for scope | Research | A | A |  | R |  |  | 2022-01-27 | 2022-01-28 | 1 | 2 |  |  | 2022-01-24 | 2022-01-25
K | 11.3 | Project Scope Document | Finalize and publish | Pack and publish | A | A |  | R |  |  | 2022-01-27 | 2022-01-28 | 1 | 1 |  |  | 2022-01-25 | 2022-01-25
L | 12.1 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Interview VPs | Create | R | A |  |  |  |  | 2022-02-03 | 2022-02-07 | 4 | 0.16667 |  |  | 2022-02-09 | 2022-02-09
L | 12.2 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Prepare interactions flow of decision | Research | R | A |  |  |  |  | 2022-02-03 | 2022-02-07 | 4 | 0.33333 |  |  | 2022-02-09 | 2022-02-09
L | 12.3 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Publish and finalize | Pack and publish | R | A |  |  |  |  | 2022-02-03 | 2022-02-07 | 4 | 0.16667 |  |  | 2022-02-09 | 2022-02-09
M | 13.1 | AS-IS principles of OHT and/or Executive Decision Making operations | Interview VPs | Create |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4 | 0.25 |  |  | 2022-02-10 | 2022-02-10
M | 13.2 | AS-IS principles of OHT and/or Executive Decision Making operations | Prepare Decision flow | Research |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4 | 0.75 |  |  | 2022-02-10 | 2022-02-10
M | 13.3 | AS-IS principles of OHT and/or Executive Decision Making operations | Publish and finalize | Package and publish |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10
N | 14.1 | To-Be persons / roles / actors and interactions of Executive Decision Making operations | Develop To-be flow | Create |  |  |  | R |  | A | 2022-02-03 | 2022-02-07 | 4 | 0.5 |  |  | 2022-02-03 | 2022-02-03
N | 14.2 | To-Be persons / roles / actors and interactions of Executive Decision Making operations | Prepare interactions flow between actors/roles/system | Research |  |  |  | R |  | A | 2022-02-03 | 2022-02-07 | 4 | 0.66667 |  |  | 2022-02-05 | 2022-02-06
N | 14.3 | To-Be persons / roles / actors and interactions of Executive Decision Making operations | Publish and finalize | Package and publish |  |  |  | R |  | A | 2022-02-03 | 2022-02-07 | 4 | 0.75 |  |  | 2022-02-07 | 2022-02-08
O | 15.1 | Executive Dashboard annotated list of elements for the dashboard, | Develop list | Create | R |  |  |  | A |  | 2022-02-05 | 2022-02-08 | 3 | 0.83333 |  |  | 2022-02-18 | 2022-02-18
O | 15.2 | Executive Dashboard annotated list of elements for the dashboard, | Publish | Package and publish | R |  |  |  | A |  | 2022-02-05 | 2022-02-08 | 3 | 0.16667 |  |  | 2022-02-18 | 2022-02-18
p | 16.1 | Possible Future Analysis and Development for Executive Decision Making Process | Develop Document | Create |  |  | A |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 1.5833 |  |  | 2022-02-15 | 2022-02-17
p | 16.2 | Possible Future Analysis and Development for Executive Decision Making Process | Analyse and collect information | Research |  |  | A |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 1.9167 |  |  | 2022-02-16 | 2022-02-17
P | 16.3 | Possible Future Analysis and Development for Executive Decision Making Process | Finalize and publish | Package and publish |  |  | A |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 0.25 |  |  | 2022-02-17 | 2022-02-17
Q | 17.1 | Measuring Success and Failure in Changing the Executive Decision Making Process | Develop Document | Create |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3 | 1.25 |  |  | 2022-01-20 | 2022-01-18
Q | 17.2 | Measuring Success and Failure in Changing the Executive Decision Making Process | Analyse and collect information | Research |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3 | 1.25 |  |  | 2022-01-20 | 2022-01-18
Q | 17.3 | Measuring Success and Failure in Changing the Executive Decision Making Process | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3 | 1 |  |  | 2022-01-20 | 2022-01-18
R | 18.1 | Probable Benefits of Changing the Executive Decision Making Process | Develop Document | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-08 | 3 | 2 |  |  | 2022-02-13 | 2022-02-13
R | 18.2 | Probable Benefits of Changing the Executive Decision Making Process | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-08 | 3 | 1 |  |  | 2022-02-13 | 2022-02-13
R | 18.3 | Probable Benefits of Changing the Executive Decision Making Process | Finalize and publish | Package and publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-08 | 3 | 1 |  |  | 2022-02-17 | 2022-02-17
S | 19.1 | Detailed References | Develop Document | Create |  |  | R | A |  |  | 2022-02-10 | 2022-02-17 | 7 | 1 |  |  | 2022-02-18 | 2022-02-18
S | 19.2 | Detailed References | Finalize and publish | Package and publish |  |  | R | A |  |  | 2022-02-10 | 2022-02-17 | 7 | 1 |  |  | 2022-02-18 | 2022-02-18
T | 20.1 | Business Challenges | Develop Document | Create | R |  | A |  |  |  | 2022-02-03 | 2022-02-10 | 7 | 0.5 |  |  | 2022-02-10 | 2022-02-10
T | 20.2 | Business Challenges | Analyse and collect information | Research | R |  | A |  |  |  | 2022-02-03 | 2022-02-10 | 7 | 1 |  |  | 2022-02-10 | 2022-02-10
T | 20.3 | Business Challenges | Finalize and publish | Package and publish | R |  | A |  |  |  | 2022-02-03 | 2022-02-10 | 7 | 0.25 |  |  | 2022-02-10 | 2022-02-10
U | 21.1 | Current Brands Involved and their Statuses | Develop Document | Create |  |  |  |  | A | R | 2022-02-03 | 2022-02-06 | 3 | 0.91667 |  |  | 2022-02-13 | 2022-02-15
U | 21.2 | Current Brands Involved and their Statuses | Analyse and collect information | Research |  |  |  |  | A | R | 2022-02-03 | 2022-02-06 | 3 | 0.66667 |  |  | 2022-02-14 | 2022-02-15
U | 21.3 | Current Brands Involved and their Statuses | Finalize and publish | Package and publish |  |  |  |  | A | R | 2022-02-03 | 2022-02-06 | 3 | 1.25 |  |  | 2022-02-15 | 2022-02-15
V | 22.1 | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | Develop Document | Create |  |  |  | R |  | A | 2022-02-04 | 2022-02-10 | 6 | 0.41667 |  |  | 2022-02-05 | 2022-02-06
V | 22.2 | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | Analyse and list out possible risks | Research |  |  |  | R |  | A | 2022-02-04 | 2022-02-10 | 6 | 0.58333 |  |  | 2022-02-07 | 2022-02-08
V | 22.3 | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | Finalize and publish | Package and publish |  |  |  | R |  | A | 2022-02-04 | 2022-02-10 | 6 | 0.53333 |  |  | 2022-02-09 | 2022-02-09
W | 23.1 | Known Client Requirements | Develop Document | Create |  | R |  |  | A |  | 2022-01-29 | 2022-02-06 | 8 | 0.66667 |  |  | 2022-01-27 | 2022-01-28
w | 23.2 | Known Client Requirements | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-01-29 | 2022-02-06 | 8 | 0.5 |  |  | 2022-01-27 | 2022-01-28
X | 24.1 | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | Develop Document | Create |  |  | R | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.33333 |  |  | 2022-01-27 | 2022-01-27
X | 24.2 | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | Analyse and document | Research |  |  | R | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.33333 |  |  | 2022-01-27 | 2022-01-27
X | 24.3 | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | Finalize and publish | Package and publish |  |  | R | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.33333 |  |  | 2022-01-28 | 2022-01-28
Y | 25.1 | Gantt Chart | Develop Document | Create | A | R |  |  | R |  | 2022-01-27 | 2022-01-28 | 1 | 6.75 |  |  | 2022-01-20 | 2022-01-28
Y | 25.2 | Gantt Chart | Analyse and plan | Research | A | R |  |  | R |  | 2022-01-27 | 2022-01-28 | 1 | 1.9167 |  |  | 2022-01-20 | 2022-01-28
Y | 25.3 | Gantt Chart | Finalize and publish | Package and publish | A | R |  |  | R |  | 2022-01-27 | 2022-01-28 | 1 | 3.1667 |  |  | 2022-01-20 | 2022-01-28
Z | 26.1 | Persona For Executive Dashbaord | Develop Document | Create |  | A |  |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 0 |  |  | 2022-02-10 | 2022-02-11
Z | 26.2 | Persona For Executive Dashbaord | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 0 |  |  | 2022-02-10 | 2022-02-11
AA | 27.1 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Develop Use case Document | Create |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.5 |  |  | 2022-02-15 | 2022-02-13
AA | 27.2 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Analyse and list out relation between actors and systems | Research |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.8333 |  |  | 2022-02-15 | 2022-02-13
AA | 27.3 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.25 |  |  | 2022-02-15 | 2022-02-13
AB | 28.1 | Gap Analysis Document | Develop Gap analysis document | Create |  |  | A |  | R |  | 2022-02-08 | 2022-02-10 | 2 | 1 |  |  | 2022-02-17 | 2022-02-17
AB | 28.2 | Gap Analysis Document | Analyse and collect information | Research |  |  | A |  | R |  | 2022-02-08 | 2022-02-10 | 2 | 0.5 |  |  | 2022-02-17 | 2022-02-17
AB | 28.3 | Gap Analysis Document | Finalize and publish | Package and publish |  |  | A |  | R |  | 2022-02-08 | 2022-02-10 | 2 | 2.15 |  |  | 2022-02-17 | 2022-02-17
AC | 29.1 | Guidance on Using the Dashboard - Video or Text+Graphics | Record video for using dashboard | Create |  | R |  |  | A |  | 2022-02-08 | 2022-02-11 | 3 | 0.33333 |  |  | 2022-02-11 | 2022-02-11
AC | 29.2 | Guidance on Using the Dashboard - Video or Text+Graphics | Show step by step guidance on using dashboard | Research |  | R |  |  | A |  | 2022-02-08 | 2022-02-11 | 3 | 0.83333 |  |  | 2022-02-11 | 2022-02-11
AC | 29.3 | Guidance on Using the Dashboard - Video or Text+Graphics | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-02-08 | 2022-02-11 | 3 | 1.8333 |  |  | 2022-02-11 | 2022-02-11
AD | 30.1 | TrackR Data Gen metric Data Sources List and DB Schema | Create source list | Create | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-11 | 2022-02-11
AD | 30.2 | TrackR Data Gen metric Data Sources List and DB Schema | analyze and collect information | Research | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-11 | 2022-02-11
AD | 30.3 | TrackR Data Gen metric Data Sources List and DB Schema | Publish | Package and publish | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-11 | 2022-02-11
AE | 31.1 | TrackR Data Gen metric Data Sources Data Overview / Profile | Create source list | Create |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-18 | 2022-02-18
AE | 31.2 | TrackR Data Gen metric Data Sources Data Overview / Profile | Publish | Package and publish |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-18 | 2022-02-18
AF | 32.1 | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Create document for style guide | Create |  | R |  |  | A |  | 2022-02-06 | 2022-02-10 | 4 | 0.25 |  |  | 2022-02-08 | 2022-02-08
AF | 32.2 | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-06 | 2022-02-10 | 4 | 0.25 |  |  | 2022-02-08 | 2022-02-08
AG | 33.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Create navigation guide wireframe for moving forward | Create |  | A |  |  |  | R | 2022-02-08 | 2022-02-10 | 2 | 0.75 |  |  | 2022-02-08 | 2022-02-10
AG | 33.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Prepare layout and finalize | Package and publish |  | A |  |  |  | R | 2022-02-08 | 2022-02-10 | 2 | 1.6667 |  |  | 2022-02-09 | 2022-02-10
AH | 34.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Create navigation guide wireframe for moving backward | Create |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2 | 0 |  |  | 2022-02-08 | 2022-02-09
AH | 34.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Prepare layout and finalize | Package and publish |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2 | 0 |  |  | 2022-02-09 | 2022-02-10
AI | 35.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Create navigation guide wireframe for Changing time frame | Create |  |  |  | A | R |  | 2022-02-08 | 2022-02-10 | 2 | 5.5 |  |  | 2022-02-10 | 2022-02-18
AI | 35.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Prepare layout and finalize | Package and publish |  |  |  | A | R |  | 2022-02-08 | 2022-02-10 | 2 | 5.5 |  |  | 2022-02-10 | 2022-02-18
AJ | 36.1 | ERD Diagram | Develop document | Create | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0.16667 |  |  | 2022-02-11 | 2022-02-11
AJ | 36.2 | ERD Diagram | Analyze and prepare erd layout | Research | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0.16667 |  |  | 2022-02-11 | 2022-02-11
AJ | 36.3 | ERD Diagram | Finalize and publish | Package and publish | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0.16667 |  |  | 2022-02-11 | 2022-02-11
AK | 37.1 | Pseudo-code Document | Develop pseudocode document | Create |  |  |  | A |  | R | 2022-02-10 | 2022-02-12 | 2 | 2.5 |  |  | 2022-02-13 | 2022-02-16
AK | 37.2 | Pseudo-code Document | Analyze and collect information | Research |  |  |  | A |  | R | 2022-02-10 | 2022-02-12 | 2 | 1.5 |  |  | 2022-02-15 | 2022-02-16
AK | 37.3 | Pseudo-code Document | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-10 | 2022-02-12 | 2 | 2 |  |  | 2022-02-16 | 2022-02-16
AL | 38.1 | Agile Development Document | Develop Agile development document | Create |  |  | R |  | A |  | 2022-02-06 | 2022-02-09 | 3 | 1.5 |  |  | 2022-02-14 | 2022-02-14
AL | 38.2 | Agile Development Document | Analyze and collect information | Research |  |  | R |  | A |  | 2022-02-06 | 2022-02-09 | 3 | 2 |  |  | 2022-02-14 | 2022-02-14
AL | 38.3 | Agile Development Document | Finalize and publish | Package and publish |  |  | R |  | A |  | 2022-02-06 | 2022-02-09 | 3 | 1 |  |  | 2022-02-17 | 2022-02-17
AM | 39.1 | Cockburn templates for all identified interactions | Develop Cockburn template | Create | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 2 |  |  | 2022-02-15 | 2022-02-13
AM | 39.2 | Cockburn templates for all identified interactions | Analyze and collect information | Research | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 3 |  |  | 2022-02-15 | 2022-02-13
AM | 39.3 | Cockburn templates for all identified interactions | Finalize and publish | Package and publish | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 1.5 |  |  | 2022-02-15 | 2022-02-13
AN | 40.1 | List, References and General Details of Suggested Metrics | Create general details of suggested metrics | Create |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 1.25 |  |  | 2022-02-18 | 2022-02-18
AN | 40.2 | List, References and General Details of Suggested Metrics | Collect all information | Research |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-18 | 2022-02-18
AN | 40.3 | List, References and General Details of Suggested Metrics | Finalize and publish | Package and publish |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-18 | 2022-02-18
AO | 41.1 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 1 | Create | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 1 |  |  | 2022-02-09 | 2022-02-09
AO | 41.2 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 1 |  |  | 2022-02-09 | 2022-02-09
AO | 41.3 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.33333 |  |  | 2022-02-10 | 2022-02-10
AP | 42.1 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 2 | Create | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 4 |  |  | 2022-02-09 | 2022-02-09
AP | 42.2 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 3.1667 |  |  | 2022-02-09 | 2022-02-10
AP | 42.3 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 0.66667 |  |  | 2022-02-10 | 2022-02-10
AQ | 43.1 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 3 | Create |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 1.25 |  |  | 2022-02-04 | 2022-02-11
AQ | 43.2 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 1.25 |  |  | 2022-02-04 | 2022-02-11
AQ | 43.3 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 1.25 |  |  | 2022-02-04 | 2022-02-11
AR | 44.1 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 4 | Create |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10 | R | R | R | R | R
AR | 44.2 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-10 | 2022-02-10
AR | 44.3 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.25 |  |  | 2022-02-10 | 2022-02-10
AS | 45.1 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 5 | Create |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 2.1667 |  |  | 2022-02-18 | 2022-02-18 | R | R | Absent | R | R
As | 45.2 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.66667 |  |  | 2022-02-10 | 2022-02-10
AS | 45.3 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10
AT | 46.1 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 6 | Create |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.66667 |  |  | 2022-02-06 | 2022-02-07
AT | 46.2 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-08 | 2022-02-09
AT | 46.3 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-09 | 2022-02-09
AU | 47.1 | Interview and/or survey of 6 OHT CPs | Develop document | Create | R | R | A |  |  |  | 2022-02-01 | 2022-02-03 | 2 | 0.25 |  |  | 2022-02-11 | 2022-02-11
AU | 47.2 | Interview and/or survey of 6 OHT CPs | Finalize document | Publish | R | R | A |  |  |  | 2022-02-01 | 2022-02-03 | 2 | 0.91667 |  |  | 2022-02-11 | 2022-02-11
AV | 48.1 | Data Listing of 6 OHT VPs Measurements of Business Success | Develop document for business success | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AV | 48.2 | Data Listing of 6 OHT VPs Measurements of Business Success | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AV | 48.3 | Data Listing of 6 OHT VPs Measurements of Business Success | Finalize and Publish | Package and Publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AW | 49.1 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Develop document for attitude towards change | Create |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-07 | 2022-02-08
AW | 49.2 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Analyse and collect information | Research |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.83333 |  |  | 2022-02-07 | 2022-02-08
AW | 49.3 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Finalize and Publish | Package and Publish |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-07 | 2022-02-08
AX | 50.1 | Data Listing of 6 OHT VPs visions for a better managed OHT | Develop document for OHT's vision for better management | Create |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0 |  |  | 2022-01-27 | 2022-02-04
AX | 50.2 | Data Listing of 6 OHT VPs visions for a better managed OHT | Analyse and collect information | Research |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0 |  |  | 2022-01-27 | 2022-02-04
AX | 50.3 | Data Listing of 6 OHT VPs visions for a better managed OHT | Finalize and Publish | Package and Publish |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0 |  |  | 2022-01-27 | 2022-02-04
AY | 51.1 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Develop document for response to meeting 3 times a week | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.2 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.3 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Finalize and Publish | Package and Publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AZ | 52.1 | Interview and/or survey of 6 OHT VPs | Develop document | Create |  | A |  |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.16667 |  |  | 2022-02-06 | 2022-02-08
AZ | 52.2 | Interview and/or survey of 6 OHT VPs | Finalize document | Publish |  | A |  |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-08 | 2022-02-08
BA | 53.1 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Gather the infromation about Monthly Finance Reports used | Research |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333 |  |  | 2022-02-05 | 2022-02-05
BA | 53.2 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Document the infromation | Create |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333 |  |  | 2022-02-06 | 2022-02-08
BA | 53.3 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Finalise the report | Publish |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.5 |  |  | 2022-02-10 | 2022-02-10
BB | 54.1 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Gather the knowledge about the Computer Based methods of Report Circulation | Research |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 3.0833 |  |  | 2022-02-05 | 2022-02-10
BB | 54.2 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | List the knowledge about the Computer Based methods of Report Circulation | Create |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 0.5 |  |  | 2022-02-06 | 2022-02-10
BB | 54.3 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Publish the knowledge | Publish |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 0.5 |  |  | 2022-02-07 | 2022-02-10
BC | 55.1 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Gather information about the computer skills, Dashboard understanding | Research |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0.66667 |  |  | 2022-02-11 | 2022-02-11
BC | 55.2 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | analyse information about the computer skills, Dashboard understanding | Create |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0.5 |  |  | 2022-02-11 | 2022-02-11
BC | 55.3 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Document the learning | Pack and Publish |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0.25 |  |  | 2022-02-11 | 2022-02-11
BD | 56.1 | Listing of 6 OHT VPs Preferred learning style | Eliciate the preferred way of learning a new concept from VP | Research |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BD | 56.2 | Listing of 6 OHT VPs Preferred learning style | identify the way of learning | Create |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BD | 56.3 | Listing of 6 OHT VPs Preferred learning style | Pack and publish preferred way of learning | Pack and Publish |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BE | 57.1 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Eliciate the preferred way of implement a new concept from VP | Research |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0 |  |  | 2022-01-27 | 2022-02-04
BE | 57.2 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Identify the way of implementation | Pack and Publish |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0 |  |  | 2022-01-27 | 2022-02-04
BE | 57.3 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Share it with a team | Pack and ublish |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0 |  |  | 2022-01-27 | 2022-02-04
BF | 58.1 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Research about the Data lakes, Data Marts, Data Warehouse, including SWOT | Research |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 1.5 |  |  | 2022-02-10 | 2022-02-10
BF | 58.2 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Create about the Data lakes, Data Marts, Data Warehouse, including SWOT | Create |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 4 |  |  | 2022-02-10 | 2022-02-10
BF | 58.3 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Pack and Publish the writtern briefing about Data lakes, Data Marts, Data Warehouse, including SWOT | Pack and publish |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 1 |  |  | 2022-02-10 | 2022-02-10
BG | 59.1 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Research about the ERP, TPS and Query tools with SWOT | Research |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 1 |  |  | 2022-02-03 | 2022-02-04
BG | 59.2 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Create about the ERP, TPS and Query tools with SWOT | Create |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 1.8333 |  |  | 2022-02-04 | 2022-02-04
BG | 59.3 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Pack and Publish the wirtten briefing about ERP, TPS and Query tools with SWOT | Pack and Publish |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 0.83333 |  |  | 2022-02-05 | 2022-02-05
BH | 60.1 | VP's Written Briefing on Executive and Analytical Dashboards | Reserach about the analytical dashboard and Executive dashboard | Research | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 1 |  |  | 2022-02-07 | 2022-02-07
BH | 60.2 | VP's Written Briefing on Executive and Analytical Dashboards | Create a report explaning analytical dashboard and Executive dashboard | Create | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 0.5 |  |  | 2022-02-07 | 2022-02-07
BH | 60.3 | VP's Written Briefing on Executive and Analytical Dashboards | Pack and Publish the Report | Pack and publish | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 0.16667 |  |  | 2022-02-07 | 2022-02-07
BI | 61.1 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 0.16667 |  |  | 2022-02-10 | 2022-02-10
BI | 61.2 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 0.66667 |  |  | 2022-02-10 | 2022-02-10
BI | 61.3 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Pack and Publish |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 1.1667 |  |  | 2022-02-10 | 2022-02-10
BJ | 62.1 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.25
BJ | 62.2 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5
BJ | 62.3 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Pack and Publish | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.63333
BK | 63.1 | suggested VP training plans | Research about the Training plan | Research | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0.66667 |  |  | 2022-02-11 | 2022-02-11
BK | 63.2 | suggested VP training plans | Create a Training plan | Create | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0.25 |  |  | 2022-02-11 | 2022-02-11
BK | 63.3 | suggested VP training plans | Execute the training plan | Execute | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0.25 |  |  | 2022-02-11 | 2022-02-11
BL | 64.1 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 1 |  |  | 2022-02-14 | 2022-02-14
BL | 64.2 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 5.5 |  |  | 2022-02-15 | 2022-02-15
BL | 64.3 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 5.5 |  |  | 2022-02-15 | 2022-02-15
BM | 65.1 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.66667 |  |  | 2022-02-07 | 2022-02-07
BM | 65.2 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5 |  |  | 2022-02-09 | 2022-02-10
BM | 65.3 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.41667 |  |  | 2022-02-10 | 2022-02-10
BN | 66.1 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10
BN | 66.2 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 1 |  |  | 2022-02-10 | 2022-02-10
BN | 66.3 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10
BO | 67.1 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.33333 |  |  | 2022-02-06 | 2022-02-06
BO | 67.2 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.41667 |  |  | 2022-02-08 | 2022-02-09
BO | 67.3 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.43333 |  |  | 2022-02-09 | 2022-02-09
BP | 68.1 | General configuration of Executive Dashboard using PowerBI | Research about the General configuration of Executive Dashboard using PowerBI | Research |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.1667 |  |  | 2022-02-17 | 2022-02-17
BP | 68.2 | General configuration of Executive Dashboard using PowerBI | Create about the General configuration of Executive Dashboard using PowerBI | Create |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.3333 |  |  | 2022-02-17 | 2022-02-17
BP | 68.3 | General configuration of Executive Dashboard using PowerBI | Pack and Publish General configuration of Executive Dashboard using PowerBI | Pack and Publish |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.91667 |  |  | 2022-02-17 | 2022-02-17
BQ | 69.1 | Executive Dashboard Metric 1 using TrackR Data Generator Data | Research about the Metric 1 | Research | R | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.75 |  |  | 2022-02-14 | 2022-02-14
BQ | 69.2 | Executive Dashboard Metric 1 using TrackR Data Generator Data | Create a Metric 1 | Create | R | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.4167 |  |  | 2022-02-14 | 2022-02-14
BQ | 69.3 | Executive Dashboard Metric 1 using TrackR Data Generator Data | Pack and Publish Metric 1 | Pack and Publish | R | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.25 |  |  | 2022-02-14 | 2022-02-14
BR | 70.1 | Executive Dashboard Metric 2 using TrackR Data Generator Data | Research about the Metric 2 | Research | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-08 | 2022-02-08
BR | 70.2 | Executive Dashboard Metric 2 using TrackR Data Generator Data | Create a Metric 2 | Create | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.41667 |  |  | 2022-02-08 | 2022-02-08
BR | 70.3 | Executive Dashboard Metric 2 using TrackR Data Generator Data | Pack and Publish Metric 2 | Pack and Publish | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.75 |  |  | 2022-02-08 | 2022-02-08
BS | 71.1 | Executive Dashboard Metric 3 using TrackR Data Generator Data | Research about the Metric 3 | Research |  | R |  |  | A |  | 2022-02-05 | 2022-02-10 | 5 | 2.3333 |  |  | 2022-02-08 | 2022-02-08
BS | 71.2 | Executive Dashboard Metric 3 using TrackR Data Generator Data | Create about the Metric 3 | Create |  | R |  |  | A |  | 2022-02-05 | 2022-02-10 | 5 | 5.4167 |  |  | 2022-02-08 | 2022-02-08
BS | 71.3 | Executive Dashboard Metric 3 using TrackR Data Generator Data | Pack and Publish Metric 3 | Pack and Publish |  | R |  |  | A |  | 2022-02-05 | 2022-02-10 | 5 | 6.5833 |  |  | 2022-02-08 | 2022-02-08
BT | 72.1 | Executive Dashboard Metric 4 | Research about the Metric 4 | Research | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-08 | 2022-02-08
BT | 72.2 | Executive Dashboard Metric 4 | Create a Metric 4 | Create | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.41667 |  |  | 2022-02-08 | 2022-02-08
BT | 72.3 | Executive Dashboard Metric 4 | Pack and Publish the metric 4 | Pack and Publish | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.75 |  |  | 2022-02-08 | 2022-02-08
BU | 73.1 | Executive Dashboard Metric 5 | Research about the Metric 5 | Research |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333 |  |  | 2022-02-08 | 2022-02-08
BU | 73.2 | Executive Dashboard Metric 5 | Create a Metric 5 | Create |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.41667 |  |  | 2022-02-08 | 2022-02-08
BU | 73.3 | Executive Dashboard Metric 5 | Pack and Publish the metric 5 | Pack and Publish |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.75 |  |  | 2022-02-09 | 2022-02-09
BV | 74.1 | Executive Dashboard Metric 6 | Research about the Metric 6 | Research |  | R |  |  |  | A | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-09 | 2022-02-09
BV | 74.2 | Executive Dashboard Metric 6 | Create a Metric 6 | Create |  | R |  |  |  | A | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-09 | 2022-02-09
BV | 74.3 | Executive Dashboard Metric 6 | Research about the Metric 6 | Pack and Publish |  | R |  |  |  | A | 2022-02-05 | 2022-02-10 | 5 | 1 |  |  | 2022-02-10 | 2022-02-10
BX | 75.1 | Merged Final Report | Create Dashboard Menu/system Map | Create | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 0 |  |  | 2022-02-10 | 2022-02-18
BW | 75.2 | Executive Dashboard menu / system map | Create Dashboard Menu/system Map | Pack and Publish |  |  |  | A | R |  | 2022-02-07 | 2022-02-12 | 5 | 0
BX | 76.1 | Merged Final Report | Gather all the inforamtion for Final Report | Research | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 7.5 |  |  | 2022-02-10 | 2/18/202
BX | 76.2 | Merged Final Report | Create Final merged Final report | Create | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 5.5 |  |  | 2022-02-10 | 2/18/202
BX | 76.3 | Merged Final Report | Edit and update all the Final Merged document | Review | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 5.5 |  |  | 2022-02-10 | 2/18/202
BX | 76.4 | Merged Final Report | Pack and Publish Final Report | Pack and Publish | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 2.5 |  |  | 2022-02-10 | 2/18/202
BY | 77.1 | Powerpoint Presentation | Gather all the information for Power Persentation | Research |  | A |  | R |  |  | 2022-02-13 | 2022-02-17 | 4 | 1 |  |  | 2022-02-13 | 2022-02-13
BY | 77.2 | Powerpoint Presentation | Create a Power Point Presentation | Create |  | A |  | R |  |  | 2022-02-13 | 2022-02-17 | 4 | 3 |  |  | 2022-02-15 | 2022-02-16
BY | 77.3 | Powerpoint Presentation | Pack and Publish all the information | Pack and Publish |  | A |  | R |  |  | 2022-02-13 | 2022-02-17 | 4 | 2.15 |  |  | 2022-02-17 | 2022-02-17
BZ | 78.1 | Final RFI report | Gather all the information for RFI Report | Research |  | A | R |  | R |  | 2022-01-28 | 2022-02-17 | 20 | 0.5 |  |  | 2022-02-18 | 2022-02-18
BZ | 78.2 | Final RFI report | Merge all the information for RFI Report | Create |  | A | R |  | R |  | 2022-01-28 | 2022-02-17 | 20 | 4.4833 |  |  | 2022-02-18 | 2022-02-18
BZ | 78.3 | Final RFI report | Publish the RFI Report | Pack and Publish |  | A | R |  | R |  | 2022-01-28 | 2022-02-17 | 20 | 1.5 |  |  | 2022-02-18 | 2022-02-18
CA | 79.1 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Research |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 3.0833 |  |  | 2022-02-10 | 2022-02-10
CA | 79.2 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Create |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 2.8333 |  |  | 2022-02-10 | 2022-02-10
CA | 79.3 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Pack and Publish |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 4.3167 |  |  | 2022-02-10 | 2022-02-10
CB | 80.1 | Time and Effort Reporting | Create a Time and Reporting sheet | Research | R | R | R | R | R | R | 2022-01-28 | 2022-02-17 | 20 | 1 |  |  | 2022-02-17 | 2022-02-18
CB | 80.2 | Time and Effort Reporting | Create a Time and Reporting sheet | Create | R | R | R | R | R | R | 2022-01-28 | 2022-02-17 | 20 | 1 |  |  | 2022-02-17 | 2022-02-18
CB | 80.3 | Time and Effort Reporting | Create a Time and Reporting sheet | Pack and Publish | R | R | R | R | R | R | 2022-01-28 | 2022-02-17 | 20 | 1 |  |  | 2022-02-17 | 2022-02-18
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
[6 empty] | Analysis of Plan R, A, C, I's: | R | 39 | 57 | 44 | 39 | 37 | 34
[7 empty] | A | 39 | 35 | 38 | 36 | 43 | 37
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | I | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Gantt sheet
TaskID | Task | Start date | End Date | Duration
J | Requests for Information with NDA (included as an Appendix) | 2022-01-20 | 2022-01-21 | 1
A | Letter of Transmittal | 2022-01-27 | 2022-01-28 | 1
B | Cover Page | 2022-01-27 | 2022-01-28 | 1
C | Page Headers, Footers and Numbering | 2022-01-27 | 2022-01-28 | 1
D | TOC | 2022-01-27 | 2022-01-28 | 1
E | Document History | 2022-01-27 | 2022-01-28 | 1
F | Executive Summary | 2022-01-27 | 2022-01-28 | 1
G | Assumptions | 2022-01-27 | 2022-01-28 | 1
H | Conclusions | 2022-01-27 | 2022-01-28 | 1
I | Background and overview of client | 2022-01-27 | 2022-01-28 | 1
K | Project Scope Document | 2022-01-27 | 2022-01-28 | 1
X | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | 2022-01-27 | 2022-01-28 | 1
Y | Gantt Chart | 2022-01-27 | 2022-01-28 | 1
BZ | Final RFI report | 2022-01-28 | 2022-02-17 | 20
CA | RACI+, Documentation, Backup Sheets | 2022-01-28 | 2022-02-18 | 21
CB | Time and Effort Reporting | 2022-01-28 | 2022-02-17 | 20
W | Known Client Requirements | 2022-01-29 | 2022-02-06 | 8
AU | Interview and/or survey of 6 OHT CPs | 2022-02-01 | 2022-02-03 | 2
L | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | 2022-02-03 | 2022-02-07 | 4
M | AS-IS principles of OHT and/or Executive Decision Making operations | 2022-02-03 | 2022-02-07 | 4
N | To-Be persons / roles / actors and interactions of Executive Decision Making operations | 2022-02-03 | 2022-02-07 | 4
T | Business Challenges | 2022-02-03 | 2022-02-10 | 7
U | Current Brands Involved and their Statuses | 2022-02-03 | 2022-02-06 | 3
BF | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | 2022-02-03 | 2022-02-06 | 3
BG | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | 2022-02-03 | 2022-02-06 | 3
BH | VP's Written Briefing on Executive and Analytical Dashboards | 2022-02-03 | 2022-02-06 | 3
V | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | 2022-02-04 | 2022-02-10 | 6
AA | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | 2022-02-04 | 2022-02-07 | 3
AJ | ERD Diagram | 2022-02-04 | 2022-02-08 | 4
O | Executive Dashboard annotated list of elements for the dashboard, | 2022-02-05 | 2022-02-08 | 3
P | Possible Future Analysis and Development for Executive Decision Making Process | 2022-02-05 | 2022-02-08 | 3
Q | Measuring Success and Failure in Changing the Executive Decision Making Process | 2022-02-05 | 2022-02-08 | 3
R | Probable Benefits of Changing the Executive Decision Making Process | 2022-02-05 | 2022-02-08 | 3
AD | TrackR Data Gen metric Data Sources List and DB Schema | 2022-02-05 | 2022-02-10 | 5
AE | TrackR Data Gen metric Data Sources Data Overview / Profile | 2022-02-05 | 2022-02-10 | 5
AM | Cockburn templates for all identified interactions | 2022-02-05 | 2022-02-08 | 3
AN | List, References and General Details of Suggested Metrics | 2022-02-05 | 2022-02-09 | 4
AO | Metric 1 - Data needed, Interpretation, Value to Decision Makers | 2022-02-05 | 2022-02-09 | 4
AP | Metric 2 - Data needed, Interpretation, Value to Decision Makers | 2022-02-05 | 2022-02-09 | 4
AQ | Metric 3 - Data needed, Interpretation, Value to Decision Makers | 2022-02-05 | 2022-02-09 | 4
AR | Metric 4 - Data needed, Interpretation, Value to Decision Makers | 2022-02-05 | 2022-02-09 | 4
AS | Metric 5 - Data needed, Interpretation, Value to Decision Makers | 2022-02-05 | 2022-02-09 | 4
AT | Metric 6 - Data needed, Interpretation, Value to Decision Makers | 2022-02-05 | 2022-02-09 | 4
AV | Data Listing of 6 OHT VPs Measurements of Business Success | 2022-02-05 | 2022-02-10 | 5
AW | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | 2022-02-05 | 2022-02-10 | 5
AX | Data Listing of 6 OHT VPs visions for a better managed OHT | 2022-02-05 | 2022-02-10 | 5
AY | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | 2022-02-05 | 2022-02-10 | 5
AZ | Interview and/or survey of 6 OHT VPs | 2022-02-05 | 2022-02-10 | 5
BA | Data Listing of 6 OHT VPs Monthly Finance Reports Used | 2022-02-05 | 2022-02-10 | 5
BP | General configuration of Executive Dashboard using PowerBI | 2022-02-05 | 2022-02-10 | 5
BQ | Executive Dashboard Metric 1 using TrackR Data Generator Data | 2022-02-05 | 2022-02-10 | 5
BR | Executive Dashboard Metric 2 using TrackR Data Generator Data | 2022-02-05 | 2022-02-10 | 5
BS | Executive Dashboard Metric 3 using TrackR Data Generator Data | 2022-02-05 | 2022-02-10 | 5
BT | Executive Dashboard Metric 4 | 2022-02-05 | 2022-02-10 | 5
BU | Executive Dashboard Metric 5 | 2022-02-05 | 2022-02-10 | 5
BV | Executive Dashboard Metric 6 | 2022-02-05 | 2022-02-10 | 5
AF | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | 2022-02-06 | 2022-02-10 | 4
AL | Agile Development Document | 2022-02-06 | 2022-02-09 | 3
BI | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | 2022-02-06 | 2022-02-10 | 4
BJ | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | 2022-02-06 | 2022-02-10 | 4
BL | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | 2022-02-06 | 2022-02-10 | 4
BM | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | 2022-02-06 | 2022-02-10 | 4
BN | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | 2022-02-06 | 2022-02-10 | 4
BO | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | 2022-02-06 | 2022-02-10 | 4
BB | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | 2022-02-07 | 2022-02-11 | 4
BC | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | 2022-02-07 | 2022-02-11 | 4
BD | Listing of 6 OHT VPs Preferred learning style | 2022-02-07 | 2022-02-11 | 4
BE | Listing of 6 OHT VPs Preferred ways to implement new concepts | 2022-02-07 | 2022-02-11 | 4
BW | Executive Dashboard menu / system map | 2022-02-07 | 2022-02-12 | 5
AB | Gap Analysis Document | 2022-02-08 | 2022-02-10 | 2
AC | Guidance on Using the Dashboard - Video or Text+Graphics | 2022-02-08 | 2022-02-11 | 3
AG | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | 2022-02-08 | 2022-02-10 | 2
AH | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | 2022-02-08 | 2022-02-10 | 2
AI | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | 2022-02-08 | 2022-02-10 | 2
S | Detailed References | 2022-02-10 | 2022-02-17 | 7
AK | Pseudo-code Document | 2022-02-10 | 2022-02-12 | 2
BK | suggested VP training plans | 2022-02-11 | 2022-02-15 | 4
BY | Powerpoint Presentation | 2022-02-13 | 2022-02-17 | 4
Z | Persona For Executive Dashbaord | 2022-02-15 | 2022-02-17 | 2
BX | Merged Final Report | 2022-02-15 | 2022-02-17 | 2
44610
Formulas:
Start date = VLOOKUP([TaskID],'RACI Deliverables'!$C7:O86,11,FALSE)
End Date = VLOOKUP([TaskID],'RACI Deliverables'!$C7:O86,12,FALSE)

## Dlvrbls Day 5-1
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2022-01-28
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak | Anusha Asokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya keesari
Deliverable Group |  | DlvID | Project Final Deliverables (RFIs and PM Docs Deliverables are optional) | Need / Requirement ID | MayurKum Plan | Prajwal Plan | Anusha A Plan | Jigeesha Plan | Cathleen Plan | Chaitanya keesari | Professor's Marking Item ID# | Start Date | Due Date (M/D/Y) | Actual Effort Days | Actual Start Date (M/D/Y) | Actual IsBuilt Date (M/D/Y) | Done On Date (M/D/Y)
GA | Building | A | Letter of Transmittal | 20 |  |  | A |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | B | Cover Page | 20 |  |  | R | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | C | Page Headers, Footers and Numbering | 20 | A | R | [5 empty] | 2022-01-27 | 2022-01-28 | 1
GA | Building | D | TOC | 20 |  |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | E | Document History | 20 |  |  |  |  | R | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | F | Executive Summary | 21 |  | A |  |  |  | R |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | G | Assumptions | 21 | R |  |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | H | Conclusions | 21 |  | R |  |  |  | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | I | Background and overview of client | 22 | A |  | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | J | Requests for Information with NDA (included as an Appendix) | 22 |  |  | A | R |  |  |  | 2022-01-20 | 2022-01-21 | 1
GA | Building | K | Project Scope Document | 24 | A | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | L | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Need7 | R | A | [5 empty] | 2022-02-03 | 2022-02-07 | 4
GA | Building | M | AS-IS principles of OHT and/or Executive Decision Making operations | Need7 |  |  | R |  | A |  |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | N | To-Be persons / roles / actors and interactions of Executive Decision Making operations | 43 |  |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | O | Executive Dashboard annotated list of elements for the dashboard, | Need6 | R |  |  |  | A |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | P | Possible Future Analysis and Development for Executive Decision Making Process | 43 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | Q | Measuring Success and Failure in Changing the Executive Decision Making Process | 44 |  | A |  |  | R |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | R | Probable Benefits of Changing the Executive Decision Making Process | 46 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | S | Detailed References | 23 |  |  | R | A |  |  |  | 2022-02-10 | 2022-02-17 | 7
GA | Building | T | Business Challenges | 26 | R |  | A |  |  |  |  | 2022-02-03 | 2022-02-10 | 7
GA | Building | U | Current Brands Involved and their Statuses | 26 |  |  |  |  | A | R |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | V | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | 26 |  |  |  | R |  | A |  | 2022-02-04 | 2022-02-10 | 6
GA | Building | W | Known Client Requirements | 41 |  | R |  |  | A |  |  | 2022-01-29 | 2022-02-06 | 8
GA | Building | X | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | 45 |  |  | R | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Y | Gantt Chart |  | A | R |  |  | R |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Z | Document Quality Check |  | R | A | [5 empty] | 2022-02-15 | 2022-02-17 | 2
GA | Building | AA | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Need22 |  |  |  | A |  | R |  | 2022-02-04 | 2022-02-07 | 3
GA | Building | AC | Guidance on Using the Dashboard - Video or Text+Graphics | Need7 |  | R |  |  | A |  |  | 2022-02-08 | 2022-02-11 | 3
GA | Building | AD | TrackR Data Gen metric Data Sources List and DB Schema | Need7 | R | [6 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | AE | TrackR Data Gen metric Data Sources Data Overview / Profile | Need7 |  | R |  | A |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AF | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Need8 |  |  |  | R | A |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | AG | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Need8 |  | A |  |  |  | R |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AH | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Need8 |  |  | A | R |  |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AI | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Need8 |  |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AJ | ERD Diagram | 49 | R | A | [5 empty] | 2022-02-04 | 2022-02-08 | 4
GA | Building | AM | Cockburn templates for all identified interactions | Need22 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | AN | List, References and General Details of Suggested Metrics | Need1 |  | R |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AO | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Need1 | R |  |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AP | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Need1 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AQ | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AR | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | R |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AS | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Need1 |  | R |  |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AT | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | A | R |  |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AU | Interview and/or survey of 6 OHT CPs | Need 2 | R | R | A |  |  |  |  | 2022-02-01 | 2022-02-03 | 2
GA | Building | AV | Data Listing of 6 OHT VPs Measurements of Business Success | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AW | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Need 2 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AX | Data Listing of 6 OHT VPs visions for a better managed OHT | Need 2 |  |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AY | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AZ | Interview and/or survey of 6 OHT VPs | Need 3 |  | A |  |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BA | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Need 3 |  |  |  | R | A |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BB | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Need 3 |  |  |  | A |  | R |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BC | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Need 3 |  | R |  |  |  | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BD | Listing of 6 OHT VPs Preferred learning style | Need 3 |  |  | R | A |  |  |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BE | Listing of 6 OHT VPs Preferred ways to implement new concepts | Need 3 |  |  |  |  | R | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BF | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Need 4 |  |  | R |  |  | A |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BG | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Need 4 |  |  |  | R | A |  |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BH | VP's Written Briefing on Executive and Analytical Dashboards | Need 4 | R | A | [5 empty] | 2022-02-03 | 2022-02-06 | 3
GA | Building | BI | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | R |  |  |  | A |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BJ | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | R |  |  | A |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BK | suggested VP training plans | Need 5 | A |  |  |  | R |  |  | 2022-02-11 | 2022-02-15 | 4
GA | Building | BL | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  |  | A |  | R |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BM | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BN | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | A | R |  |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BO | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | A |  |  | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BP | General configuration of Executive Dashboard using PowerBI | Need 6 |  | R | A |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GF | Closing | CA | RACI+, Documentation, Backup Sheets |  |  | R |  |  | A |  |  | 2022-01-28 | 2022-02-18 | 21
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
|  |  |  | R | 11 | 13 | 12 | 13 | 8 | 11
|  |  |  | A | 11 | 10 | 10 | 11 | 13 | 11
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Tasks Day 5-1
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2020-09-17 | 3 | 2
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari | [9 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari
DlvID | TaskID | Project Final Deliverables (No Verb Words at the start) | Activity / Task (VERB: Subject) | Project Phase (see WBS) | MayurKumar | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany | Start Date | Due Date (M/D/Y) | Actual Effort (Days) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | 1.1 | Letter of Transmittal | Develop a cover page | Create | R |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 0
A | 1.2 | Letter of Transmittal | Develop a cover page | Pack and publish | R |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 0
B | 2.1 | Cover Page | Develop a cover letter | Create |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.16667 |  |  |  |  | R | C | C
B | 2.2 | Cover Page | Develop a cover letter | Pack and publish |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0.16667
C | 3.1 | Page Headers, Footers and Numbering | Develop a header, footer and numbering | Create | A | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 0
C | 3.2 | Page Headers, Footers and Numbering | Develop header, footer and numbering | Pack and publish | A | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 0
D | 4.1 | TOC | Create a table of content | Publish |  |  |  | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.25
E | 5.1 | Document History | Research about documnent history document | Research |  |  |  |  | R | A | 2022-01-27 | 2022-01-28 | 1 | 0
E | 5.2 | Document History | Develoop document history document | Create |  |  |  |  | R | A | 2022-01-27 | 2022-01-28 | 1 | 0
E | 5.3 | Document History | Publish document history document | Publish |  |  |  |  | R | A | 2022-01-27 | 2022-01-28 | 1 | 0
F | 6.1 | Executive Summary | Write summary for executives | Create |  |  | R |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 1
F | 6.2 | Executive Summary | publish summary for executive summary | Publish |  |  | R |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 0.5
G | 7.1 | Assumptions | Gather assumptions | Research | R |  |  | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0
G | 7.2 | Assumptions | Create asuumptions | Create | R |  |  | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0
G | 7.3 | Assumptions | Publish assumptions | Pack and publish | R |  |  | A |  |  | 2022-01-27 | 2022-01-28 | 1 | 0
H | 8.1 | Conclusions | Create conclusion | Create |  | R |  |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 0
H | 8.2 | Conclusions | Publish conclusion | Publish |  | R |  |  |  | A | 2022-01-27 | 2022-01-28 | 1 | 0
I | 9.1 | Background and overview of client | Develop document | Create | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 2.5
I | 9.2 | Background and overview of client | Publish final document | Publish | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1 | 1.5
J | 10.1 | Requests for Information with NDA (included as an Appendix) | Create RFI Document | Create |  |  | A | R |  |  | 2022-01-20 | 2022-01-21 | 1 | 5.5833
J | 10.2 | Requests for Information with NDA (included as an Appendix) | Look out for questions need to ask | Research |  |  | A | R |  |  | 2022-01-20 | 2022-01-21 | 1 | 5.9167
J | 10.3 | Requests for Information with NDA (included as an Appendix) | Prepare Final RFI Document | Pack and publish |  |  | A | R |  |  | 2022-01-20 | 2022-01-21 | 1 | 6
K | 11.1 | Project Scope Document | Creating Document | Create | A | A |  | R |  |  | 2022-01-27 | 2022-01-28 | 1 | 1
K | 11.2 | Project Scope Document | Develop content for scope | Research | A | A |  | R |  |  | 2022-01-27 | 2022-01-28 | 1 | 2
K | 11.3 | Project Scope Document | Finalize and publish | Pack and publish | A | A |  | R |  |  | 2022-01-27 | 2022-01-28 | 1 | 1
L | 12.1 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Interview VPs | Create | R | A |  |  |  |  | 2022-02-03 | 2022-02-07 | 4 | 0
L | 12.2 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Prepare interactions flow of decision | Research | R | A |  |  |  |  | 2022-02-03 | 2022-02-07 | 4 | 0
L | 12.3 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Publish and finalize | Pack and publish | R | A |  |  |  |  | 2022-02-03 | 2022-02-07 | 4 | 0
M | 13.1 | AS-IS principles of OHT and/or Executive Decision Making operations | Interview VPs | Create |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4 | 0.25
M | 13.2 | AS-IS principles of OHT and/or Executive Decision Making operations | Prepare Decision flow | Research |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4 | 0.75
M | 13.3 | AS-IS principles of OHT and/or Executive Decision Making operations | Publish and finalize | Package and publish |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4 | 0.5
N | 14.1 | To-Be persons / roles / actors and interactions of Executive Decision Making operations | Develop To-be flow | Create |  |  |  | R |  | A | 2022-02-03 | 2022-02-07 | 4 | 0.5
N | 14.2 | To-Be persons / roles / actors and interactions of Executive Decision Making operations | Prepare interactions flow between actors/roles/system | Research |  |  |  | R |  | A | 2022-02-03 | 2022-02-07 | 4 | 0.66667
N | 14.3 | To-Be persons / roles / actors and interactions of Executive Decision Making operations | Publish and finalize | Package and publish |  |  |  | R |  | A | 2022-02-03 | 2022-02-07 | 4 | 0.75
O | 15.1 | Executive Dashboard annotated list of elements for the dashboard, | Develop list | Create | R |  |  |  | A |  | 2022-02-05 | 2022-02-08 | 3 | 0
O | 15.2 | Executive Dashboard annotated list of elements for the dashboard, | Publish | Package and publish | R |  |  |  | A |  | 2022-02-05 | 2022-02-08 | 3 | 0
p | 16.1 | Possible Future Analysis and Development for Executive Decision Making Process | Develop Document | Create |  |  | A |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 1.5833
p | 16.2 | Possible Future Analysis and Development for Executive Decision Making Process | Analyse and collect information | Research |  |  | A |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 1.9167
P | 16.3 | Possible Future Analysis and Development for Executive Decision Making Process | Finalize and publish | Package and publish |  |  | A |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 0.25
Q | 17.1 | Measuring Success and Failure in Changing the Executive Decision Making Process | Develop Document | Create |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3 | 0
Q | 17.2 | Measuring Success and Failure in Changing the Executive Decision Making Process | Analyse and collect information | Research |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3 | 0
Q | 17.3 | Measuring Success and Failure in Changing the Executive Decision Making Process | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3 | 0
R | 18.1 | Probable Benefits of Changing the Executive Decision Making Process | Develop Document | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-08 | 3 | 2
R | 18.2 | Probable Benefits of Changing the Executive Decision Making Process | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-08 | 3 | 1
R | 18.3 | Probable Benefits of Changing the Executive Decision Making Process | Finalize and publish | Package and publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-08 | 3 | 1
S | 19.1 | Detailed References | Develop Document | Create |  |  | R | A |  |  | 2022-02-10 | 2022-02-17 | 7 | 1
S | 19.2 | Detailed References | Finalize and publish | Package and publish |  |  | R | A |  |  | 2022-02-10 | 2022-02-17 | 7 | 1
T | 20.1 | Business Challenges | Develop Document | Create | R |  | A |  |  |  | 2022-02-03 | 2022-02-10 | 7 | 0
T | 20.2 | Business Challenges | Analyse and collect information | Research | R |  | A |  |  |  | 2022-02-03 | 2022-02-10 | 7 | 0
T | 20.3 | Business Challenges | Finalize and publish | Package and publish | R |  | A |  |  |  | 2022-02-03 | 2022-02-10 | 7 | 0
U | 21.1 | Current Brands Involved and their Statuses | Develop Document | Create |  |  |  |  | A | R | 2022-02-03 | 2022-02-06 | 3 | 0.91667
U | 21.2 | Current Brands Involved and their Statuses | Analyse and collect information | Research |  |  |  |  | A | R | 2022-02-03 | 2022-02-06 | 3 | 0.66667
U | 21.3 | Current Brands Involved and their Statuses | Finalize and publish | Package and publish |  |  |  |  | A | R | 2022-02-03 | 2022-02-06 | 3 | 1.25
V | 22.1 | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | Develop Document | Create |  |  |  | R |  | A | 2022-02-04 | 2022-02-10 | 6 | 0.41667
V | 22.2 | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | Analyse and list out possible risks | Research |  |  |  | R |  | A | 2022-02-04 | 2022-02-10 | 6 | 0.58333
V | 22.3 | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | Finalize and publish | Package and publish |  |  |  | R |  | A | 2022-02-04 | 2022-02-10 | 6 | 0.53333
W | 23.1 | Known Client Requirements | Develop Document | Create |  | R |  |  | A |  | 2022-01-29 | 2022-02-06 | 8 | 0
w | 23.2 | Known Client Requirements | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-01-29 | 2022-02-06 | 8 | 0
X | 24.1 | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | Develop Document | Create |  |  | R | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.33333
X | 24.2 | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | Analyse and document | Research |  |  | R | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.33333
X | 24.3 | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | Finalize and publish | Package and publish |  |  | R | R | A |  | 2022-01-27 | 2022-01-28 | 1 | 0.33333
Y | 25.1 | Gantt Chart | Develop Document | Create | A | R |  |  | R |  | 2022-01-27 | 2022-01-28 | 1 | 0.25
Y | 25.2 | Gantt Chart | Analyse and plan | Research | A | R |  |  | R |  | 2022-01-27 | 2022-01-28 | 1 | 0.91667
Y | 25.3 | Gantt Chart | Finalize and publish | Package and publish | A | R |  |  | R |  | 2022-01-27 | 2022-01-28 | 1 | 0.66667
Z | 26.1 | Persona For Executive Dashbaord | Develop Document | Create |  | A |  |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 0
Z | 26.2 | Persona For Executive Dashbaord | Finalize and publish | Package and publish |  | A |  |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 0
AA | 27.1 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Develop Use case Document | Create |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.5
AA | 27.2 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Analyse and list out relation between actors and systems | Research |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.8333
AA | 27.3 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.25
AC | 29.1 | Guidance on Using the Dashboard - Video or Text+Graphics | Record video for using dashboard | Create |  | R |  |  | A |  | 2022-02-08 | 2022-02-11 | 3 | 0.33333
AC | 29.2 | Guidance on Using the Dashboard - Video or Text+Graphics | Show step by step guidance on using dashboard | Research |  | R |  |  | A |  | 2022-02-08 | 2022-02-11 | 3 | 0.83333
AC | 29.3 | Guidance on Using the Dashboard - Video or Text+Graphics | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-02-08 | 2022-02-11 | 3 | 1.8333
AD | 30.1 | TrackR Data Gen metric Data Sources List and DB Schema | Create source list | Create | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5 | 0
AD | 30.2 | TrackR Data Gen metric Data Sources List and DB Schema | analyze and collect information | Research | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5 | 0
AD | 30.3 | TrackR Data Gen metric Data Sources List and DB Schema | Publish | Package and publish | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5 | 0
AE | 31.1 | TrackR Data Gen metric Data Sources Data Overview / Profile | Create source list | Create |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AE | 31.2 | TrackR Data Gen metric Data Sources Data Overview / Profile | Publish | Package and publish |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AF | 32.1 | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Create document for style guide | Create |  | R |  |  | A |  | 2022-02-06 | 2022-02-10 | 4 | 0
AF | 32.2 | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-06 | 2022-02-10 | 4 | 0
AG | 33.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Create navigation guide wireframe for moving forward | Create |  | A |  |  |  | R | 2022-02-08 | 2022-02-10 | 2 | 0.75
AG | 33.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Prepare layout and finalize | Package and publish |  | A |  |  |  | R | 2022-02-08 | 2022-02-10 | 2 | 1.6667
AH | 34.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Create navigation guide wireframe for moving backward | Create |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2 | 0
AH | 34.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Prepare layout and finalize | Package and publish |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2 | 0
AI | 35.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Create navigation guide wireframe for Changing time frame | Create |  |  |  | A | R |  | 2022-02-08 | 2022-02-10 | 2 | 0
AI | 35.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Prepare layout and finalize | Package and publish |  |  |  | A | R |  | 2022-02-08 | 2022-02-10 | 2 | 0
AJ | 36.1 | ERD Diagram | Develop document | Create | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0
AJ | 36.2 | ERD Diagram | Analyze and prepare erd layout | Research | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0
AJ | 36.3 | ERD Diagram | Finalize and publish | Package and publish | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0
AM | 39.1 | Cockburn templates for all identified interactions | Develop Cockburn template | Create | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 2
AM | 39.2 | Cockburn templates for all identified interactions | Analyze and collect information | Research | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 3
AM | 39.3 | Cockburn templates for all identified interactions | Finalize and publish | Package and publish | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 1.5
AN | 40.1 | List, References and General Details of Suggested Metrics | Create general details of suggested metrics | Create |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 1.25
AN | 40.2 | List, References and General Details of Suggested Metrics | Collect all information | Research |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.75
AN | 40.3 | List, References and General Details of Suggested Metrics | Finalize and publish | Package and publish |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.75
AO | 41.1 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 1 | Create | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0
AO | 41.2 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0
AO | 41.3 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0
AP | 42.1 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 2 | Create | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 4
AP | 42.2 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 3.1667
AP | 42.3 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 0.66667
AQ | 43.1 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 3 | Create |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 0
AQ | 43.2 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 0
AQ | 43.3 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 0
AR | 44.1 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 4 | Create |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.5 |  |  | 2017-09-08 | 2017-09-08 | R | R | R | R | R
AR | 44.2 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.75
AR | 44.3 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.25
AS | 45.1 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 5 | Create |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 2.1667 |  |  | 2017-09-14 | 2017-09-14 | R | R | Absent | R | R
As | 45.2 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.66667
AS | 45.3 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.5
AT | 46.1 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 6 | Create |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.66667
AT | 46.2 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.75
AT | 46.3 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.75
AU | 47.1 | Interview and/or survey of 6 OHT CPs | Develop document | Create | R | R | A |  |  |  | 2022-02-01 | 2022-02-03 | 2 | 0
AU | 47.2 | Interview and/or survey of 6 OHT CPs | Finalize document | Publish | R | R | A |  |  |  | 2022-02-01 | 2022-02-03 | 2 | 0
AV | 48.1 | Data Listing of 6 OHT VPs Measurements of Business Success | Develop document for business success | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AV | 48.2 | Data Listing of 6 OHT VPs Measurements of Business Success | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AV | 48.3 | Data Listing of 6 OHT VPs Measurements of Business Success | Finalize and Publish | Package and Publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AW | 49.1 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Develop document for attitude towards change | Create |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0
AW | 49.2 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Analyse and collect information | Research |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0
AW | 49.3 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Finalize and Publish | Package and Publish |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0
AX | 50.1 | Data Listing of 6 OHT VPs visions for a better managed OHT | Develop document for OHT's vision for better management | Create |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0
AX | 50.2 | Data Listing of 6 OHT VPs visions for a better managed OHT | Analyse and collect information | Research |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0
AX | 50.3 | Data Listing of 6 OHT VPs visions for a better managed OHT | Finalize and Publish | Package and Publish |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.1 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Develop document for response to meeting 3 times a week | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.2 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.3 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Finalize and Publish | Package and Publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AZ | 52.1 | Interview and/or survey of 6 OHT VPs | Develop document | Create |  | A |  |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0
AZ | 52.2 | Interview and/or survey of 6 OHT VPs | Finalize document | Publish |  | A |  |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0
BA | 53.1 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Gather the infromation about Monthly Finance Reports used | Research |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333
BA | 53.2 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Document the infromation | Create |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333
BA | 53.3 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Finalise the report | Publish |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.5
BB | 54.1 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Gather the knowledge about the Computer Based methods of Report Circulation | Research |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 0
BB | 54.2 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | List the knowledge about the Computer Based methods of Report Circulation | Create |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 0
BB | 54.3 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Publish the knowledge | Publish |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 0
BC | 55.1 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Gather information about the computer skills, Dashboard understanding | Research |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0
BC | 55.2 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | analyse information about the computer skills, Dashboard understanding | Create |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0
BC | 55.3 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Document the learning | Pack and Publish |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0
BD | 56.1 | Listing of 6 OHT VPs Preferred learning style | Eliciate the preferred way of learning a new concept from VP | Research |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BD | 56.2 | Listing of 6 OHT VPs Preferred learning style | identify the way of learning | Create |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BD | 56.3 | Listing of 6 OHT VPs Preferred learning style | Pack and publish preferred way of learning | Pack and Publish |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BE | 57.1 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Eliciate the preferred way of implement a new concept from VP | Research |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0
BE | 57.2 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Identify the way of implementation | Pack and Publish |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0
BE | 57.3 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Share it with a team | Pack and ublish |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0
BF | 58.1 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Research about the Data lakes, Data Marts, Data Warehouse, including SWOT | Research |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 1.5
BF | 58.2 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Create about the Data lakes, Data Marts, Data Warehouse, including SWOT | Create |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 4
BF | 58.3 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Pack and Publish the writtern briefing about Data lakes, Data Marts, Data Warehouse, including SWOT | Pack and publish |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 1
BG | 59.1 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Research about the ERP, TPS and Query tools with SWOT | Research |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 1
BG | 59.2 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Create about the ERP, TPS and Query tools with SWOT | Create |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 1.8333
BG | 59.3 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Pack and Publish the wirtten briefing about ERP, TPS and Query tools with SWOT | Pack and Publish |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 0.83333
BH | 60.1 | VP's Written Briefing on Executive and Analytical Dashboards | Reserach about the analytical dashboard and Executive dashboard | Research | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 0
BH | 60.2 | VP's Written Briefing on Executive and Analytical Dashboards | Create a report explaning analytical dashboard and Executive dashboard | Create | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 0
BH | 60.3 | VP's Written Briefing on Executive and Analytical Dashboards | Pack and Publish the Report | Pack and publish | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 0
BI | 61.1 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 0.16667
BI | 61.2 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 0.66667
BI | 61.3 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Pack and Publish |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 1.1667
BJ | 62.1 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0
BJ | 62.2 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0
BJ | 62.3 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Pack and Publish | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0
BK | 63.1 | suggested VP training plans | Research about the Training plan | Research | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0
BK | 63.2 | suggested VP training plans | Create a Training plan | Create | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0
BK | 63.3 | suggested VP training plans | Execute the training plan | Execute | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0
BL | 64.1 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 0
BL | 64.2 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 0
BL | 64.3 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 0
BM | 65.1 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.66667
BM | 65.2 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5
BM | 65.3 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.41667
BN | 66.1 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5
BN | 66.2 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 1
BN | 66.3 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5
BO | 67.1 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.33333
BO | 67.2 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.41667
BO | 67.3 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.43333
BP | 68.1 | General configuration of Executive Dashboard using PowerBI | Research about the General configuration of Executive Dashboard using PowerBI | Research |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.1667
BP | 68.2 | General configuration of Executive Dashboard using PowerBI | Create about the General configuration of Executive Dashboard using PowerBI | Create |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.3333
BP | 68.3 | General configuration of Executive Dashboard using PowerBI | Pack and Publish General configuration of Executive Dashboard using PowerBI | Pack and Publish |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.91667
CA | 79.1 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Research |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 2.5
CA | 79.2 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Create |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 2.25
CA | 79.3 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Pack and Publish |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 3.5
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
[6 empty] | Analysis of Plan R, A, C, I's: | R | 33 | 36 | 35 | 33 | 22 | 28
[7 empty] | A | 28 | 24 | 27 | 29 | 37 | 34
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | I | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Dlvrbls Day 6-1
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2022-01-28
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak | Anusha Asokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya keesari
Deliverable Group |  | DlvID | Project Final Deliverables (RFIs and PM Docs Deliverables are optional) | Need / Requirement ID | MayurKum Plan | Prajwal Plan | Anusha A Plan | Jigeesha Plan | Cathleen Plan | Chaitanya keesari | Professor's Marking Item ID# | Start Date | Due Date (M/D/Y) | Actual Effort Days | Actual Start Date (M/D/Y) | Actual IsBuilt Date (M/D/Y) | Done On Date (M/D/Y)
GA | Building | AA | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Need22 |  |  |  | A |  | R |  | 2022-02-04 | 2022-02-07 | 3
GA | Building | AB | Gap Analysis Document | Need7 |  |  | A |  | R |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AF | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Need8 |  | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | AG | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Need8 |  | A |  |  |  | R |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AH | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Need8 |  |  | A | R |  |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AI | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Need8 |  |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AJ | ERD Diagram | 49 | R | A | [5 empty] | 2022-02-04 | 2022-02-08 | 4
GA | Building | AK | Pseudo-code Document | Need6 |  |  |  | A |  | R |  | 2022-02-10 | 2022-02-12 | 2
GA | Building | AL | Agile Development Document | 51 |  |  | R |  | A |  |  | 2022-02-06 | 2022-02-09 | 3
GA | Building | AM | Cockburn templates for all identified interactions | Need22 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | AN | List, References and General Details of Suggested Metrics | Need1 |  | R |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AO | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Need1 | R |  |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AP | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Need1 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AQ | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AR | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | R |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AS | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Need1 |  | R |  |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AT | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | A | R |  |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AU | Interview and/or survey of 6 OHT CPs | Need 2 | R | R | A |  |  |  |  | 2022-02-01 | 2022-02-03 | 2
GA | Building | AV | Data Listing of 6 OHT VPs Measurements of Business Success | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AW | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Need 2 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AX | Data Listing of 6 OHT VPs visions for a better managed OHT | Need 2 |  |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AY | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AZ | Interview and/or survey of 6 OHT VPs | Need 3 |  | A |  |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BA | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Need 3 |  |  |  | R | A |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BB | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Need 3 |  |  |  | A |  | R |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BC | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Need 3 |  | R |  |  |  | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BD | Listing of 6 OHT VPs Preferred learning style | Need 3 |  |  | R | A |  |  |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BE | Listing of 6 OHT VPs Preferred ways to implement new concepts | Need 3 |  |  |  |  | R | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BF | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Need 4 |  |  | R |  |  | A |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BG | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Need 4 |  |  |  | R | A |  |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BH | VP's Written Briefing on Executive and Analytical Dashboards | Need 4 | R | A | [5 empty] | 2022-02-03 | 2022-02-06 | 3
GA | Building | BI | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | R |  |  |  | A |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BJ | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | R |  |  | A |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BK | suggested VP training plans | Need 5 | R |  |  |  | A |  |  | 2022-02-11 | 2022-02-15 | 4
GA | Building | BL | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  |  | A |  | R |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BM | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BN | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | A | R |  |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BO | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | A |  |  | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BP | General configuration of Executive Dashboard using PowerBI | Need 6 |  | R | A |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BQ | Executive Dashboard Metric 1 using TrackR Data Generator Data | Need 6 | R | R | A |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BR | Executive Dashboard Metric 2 using TrackR Data Generator Data | Need 6 | A | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | BS | Executive Dashboard Metric 3 using TrackR Data Generator Data | Need 6 |  | R |  |  | A |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BT | Executive Dashboard Metric 4 | Need 6 | A | R | [5 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | BU | Executive Dashboard Metric 5 | Need 6 |  | R |  | A |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BV | Executive Dashboard Metric 6 | Need 6 |  | R |  |  |  | A |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BW | Executive Dashboard menu / system map | Need 6 |  |  |  | A | R |  |  | 2022-02-07 | 2022-02-12 | 5
GF | Closing | BX | Merged Final Report |  | A | A | A |  | R |  |  | 2022-02-15 | 2022-02-17 | 2
GF | Closing | BY | Powerpoint Presentation |  |  | A |  | R |  |  |  | 2022-02-13 | 2022-02-17 | 4
GF | Closing | BZ | Final RFI report |  |  | A | R |  | R |  |  | 2022-01-28 | 2022-02-17 | 20
GF | Closing | CA | RACI+, Documentation, Backup Sheets |  |  | R |  |  | A |  |  | 2022-01-28 | 2022-02-18 | 21
GF | Closing | CB | Time and Effort Reporting |  | R | R | R | R | R | R |  | 2022-01-28 | 2022-02-17 | 20
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
|  |  |  | R | 8 | 15 | 9 | 8 | 9 | 10
|  |  |  | A | 8 | 8 | 9 | 10 | 9 | 8
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Tasks Day 6-1
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2020-09-17 | 3 | 2
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari | [9 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari
DlvID | TaskID | Project Final Deliverables (No Verb Words at the start) | Activity / Task (VERB: Subject) | Project Phase (see WBS) | MayurKumar | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany | Start Date | Due Date (M/D/Y) | Actual Effort (Days) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
AA | 27.1 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Develop Use case Document | Create |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.5 |  |  | 2022-02-15 | 2022-02-13
AA | 27.2 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Analyse and list out relation between actors and systems | Research |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.8333 |  |  | 2022-02-15 | 2022-02-13
AA | 27.3 | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-04 | 2022-02-07 | 3 | 1.25 |  |  | 2022-02-15 | 2022-02-13
AB | 28.1 | Gap Analysis Document | Develop Gap analysis document | Create |  |  | A |  | R |  | 2022-02-08 | 2022-02-10 | 2 | 1
AB | 28.2 | Gap Analysis Document | Analyse and collect information | Research |  |  | A |  | R |  | 2022-02-08 | 2022-02-10 | 2 | 0.5
AB | 28.3 | Gap Analysis Document | Finalize and publish | Package and publish |  |  | A |  | R |  | 2022-02-08 | 2022-02-10 | 2 | 2.15
AF | 32.1 | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Create document for style guide | Create |  | R |  |  | A |  | 2022-02-06 | 2022-02-10 | 4 | 0.25 |  |  | 2022-02-08 | 2022-02-08
AF | 32.2 | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-06 | 2022-02-10 | 4 | 0.25 |  |  | 2022-02-08 | 2022-02-08
AG | 33.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Create navigation guide wireframe for moving forward | Create |  | A |  |  |  | R | 2022-02-08 | 2022-02-10 | 2 | 0.75 |  |  | 2022-02-08 | 2022-02-10
AG | 33.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Prepare layout and finalize | Package and publish |  | A |  |  |  | R | 2022-02-08 | 2022-02-10 | 2 | 1.6667 |  |  | 2022-02-09 | 2022-02-10
AH | 34.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Create navigation guide wireframe for moving backward | Create |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2 | 0
AH | 34.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Prepare layout and finalize | Package and publish |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2 | 0
AI | 35.1 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Create navigation guide wireframe for Changing time frame | Create |  |  |  | A | R |  | 2022-02-08 | 2022-02-10 | 2 | 5.5
AI | 35.2 | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Prepare layout and finalize | Package and publish |  |  |  | A | R |  | 2022-02-08 | 2022-02-10 | 2 | 5.5
AJ | 36.1 | ERD Diagram | Develop document | Create | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0.16667 |  |  | 2022-02-11 | 2022-02-11
AJ | 36.2 | ERD Diagram | Analyze and prepare erd layout | Research | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0.16667 |  |  | 2022-02-11 | 2022-02-11
AJ | 36.3 | ERD Diagram | Finalize and publish | Package and publish | R | A |  |  |  |  | 2022-02-04 | 2022-02-08 | 4 | 0.16667 |  |  | 2022-02-11 | 2022-02-11
AK | 37.1 | Pseudo-code Document | Develop pseudocode document | Create |  |  |  | A |  | R | 2022-02-10 | 2022-02-12 | 2 | 2.5 |  |  | 2022-02-13 | 2022-02-16
AK | 37.2 | Pseudo-code Document | Analyze and collect information | Research |  |  |  | A |  | R | 2022-02-10 | 2022-02-12 | 2 | 1.5 |  |  | 2022-02-15 | 2022-02-16
AK | 37.3 | Pseudo-code Document | Finalize and publish | Package and publish |  |  |  | A |  | R | 2022-02-10 | 2022-02-12 | 2 | 2 |  |  | 2022-02-16 | 2022-02-16
AL | 38.1 | Agile Development Document | Develop Agile development document | Create |  |  | R |  | A |  | 2022-02-06 | 2022-02-09 | 3 | 1.5 |  |  | 2022-02-14 | 2022-02-14
AL | 38.2 | Agile Development Document | Analyze and collect information | Research |  |  | R |  | A |  | 2022-02-06 | 2022-02-09 | 3 | 2 |  |  | 2022-02-14 | 2022-02-14
AL | 38.3 | Agile Development Document | Finalize and publish | Package and publish |  |  | R |  | A |  | 2022-02-06 | 2022-02-09 | 3 | 1 |  |  | 2022-02-17 | 2022-02-17
AM | 39.1 | Cockburn templates for all identified interactions | Develop Cockburn template | Create | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 2 |  |  | 2022-02-15 | 2022-02-13
AM | 39.2 | Cockburn templates for all identified interactions | Analyze and collect information | Research | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 3 |  |  | 2022-02-15 | 2022-02-13
AM | 39.3 | Cockburn templates for all identified interactions | Finalize and publish | Package and publish | A |  |  |  |  | R | 2022-02-05 | 2022-02-08 | 3 | 1.5 |  |  | 2022-02-15 | 2022-02-13
AN | 40.1 | List, References and General Details of Suggested Metrics | Create general details of suggested metrics | Create |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 1.25 |  |  | 2022-02-18 | 2022-02-18
AN | 40.2 | List, References and General Details of Suggested Metrics | Collect all information | Research |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-18 | 2022-02-18
AN | 40.3 | List, References and General Details of Suggested Metrics | Finalize and publish | Package and publish |  | R |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-18 | 2022-02-18
AO | 41.1 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 1 | Create | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 1 |  |  | 2022-02-09 | 2022-02-09
AO | 41.2 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 1 |  |  | 2022-02-09 | 2022-02-09
AO | 41.3 | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish | R |  |  |  |  | A | 2022-02-05 | 2022-02-09 | 4 | 0.33333 |  |  | 2022-02-10 | 2022-02-10
AP | 42.1 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 2 | Create | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 4 |  |  | 2022-02-09 | 2022-02-09
AP | 42.2 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 3.1667 |  |  | 2022-02-09 | 2022-02-10
AP | 42.3 | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish | A |  |  |  |  | R | 2022-02-05 | 2022-02-09 | 4 | 0.66667 |  |  | 2022-02-10 | 2022-02-10
AQ | 43.1 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 3 | Create |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 1.25
AQ | 43.2 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 1.25
AQ | 43.3 | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  |  | A | R |  | 2022-02-05 | 2022-02-09 | 4 | 1.25
AR | 44.1 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 4 | Create |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10 | R | R | R | R | R
AR | 44.2 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.75 |  |  | 2022-02-10 | 2022-02-10
AR | 44.3 | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  | R |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.25 |  |  | 2022-02-10 | 2022-02-10
AS | 45.1 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 5 | Create |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 2.1667 |  |  | 2022-02-18 | 2022-02-18 | R | R | Absent | R | R
As | 45.2 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.66667 |  |  | 2022-02-10 | 2022-02-10
AS | 45.3 | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  | R |  |  | A |  | 2022-02-05 | 2022-02-09 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10
AT | 46.1 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Develop document for Metric 6 | Create |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.66667
AT | 46.2 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Analyze and identify metric | Research |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.75
AT | 46.3 | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Prepare and Finalize | Package and publish |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4 | 0.75
AU | 47.1 | Interview and/or survey of 6 OHT CPs | Develop document | Create | R | R | A |  |  |  | 2022-02-01 | 2022-02-03 | 2 | 0.25 |  |  | 2022-02-11 | 2022-02-11
AU | 47.2 | Interview and/or survey of 6 OHT CPs | Finalize document | Publish | R | R | A |  |  |  | 2022-02-01 | 2022-02-03 | 2 | 0.91667 |  |  | 2022-02-11 | 2022-02-11
AV | 48.1 | Data Listing of 6 OHT VPs Measurements of Business Success | Develop document for business success | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AV | 48.2 | Data Listing of 6 OHT VPs Measurements of Business Success | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AV | 48.3 | Data Listing of 6 OHT VPs Measurements of Business Success | Finalize and Publish | Package and Publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AW | 49.1 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Develop document for attitude towards change | Create |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-07 | 2022-02-08
AW | 49.2 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Analyse and collect information | Research |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.83333 |  |  | 2022-02-07 | 2022-02-08
AW | 49.3 | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Finalize and Publish | Package and Publish |  |  | A |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-07 | 2022-02-08
AX | 50.1 | Data Listing of 6 OHT VPs visions for a better managed OHT | Develop document for OHT's vision for better management | Create |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0
AX | 50.2 | Data Listing of 6 OHT VPs visions for a better managed OHT | Analyse and collect information | Research |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0
AX | 50.3 | Data Listing of 6 OHT VPs visions for a better managed OHT | Finalize and Publish | Package and Publish |  |  |  |  | R | A | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.1 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Develop document for response to meeting 3 times a week | Create | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.2 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Analyse and collect information | Research | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AY | 51.3 | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Finalize and Publish | Package and Publish | A |  | R |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0
AZ | 52.1 | Interview and/or survey of 6 OHT VPs | Develop document | Create |  | A |  |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.16667 |  |  | 2022-02-06 | 2022-02-08
AZ | 52.2 | Interview and/or survey of 6 OHT VPs | Finalize document | Publish |  | A |  |  |  | R | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-08 | 2022-02-08
BA | 53.1 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Gather the infromation about Monthly Finance Reports used | Research |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333
BA | 53.2 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Document the infromation | Create |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333
BA | 53.3 | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Finalise the report | Publish |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5 | 0.5
BB | 54.1 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Gather the knowledge about the Computer Based methods of Report Circulation | Research |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 3.0833 |  |  | 2022-02-05 | 2022-02-10
BB | 54.2 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | List the knowledge about the Computer Based methods of Report Circulation | Create |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 0.5 |  |  | 2022-02-06 | 2022-02-10
BB | 54.3 | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Publish the knowledge | Publish |  |  |  | A |  | R | 2022-02-07 | 2022-02-11 | 4 | 0.5 |  |  | 2022-02-07 | 2022-02-10
BC | 55.1 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Gather information about the computer skills, Dashboard understanding | Research |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0.66667 |  |  | 2022-02-11 | 2022-02-11
BC | 55.2 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | analyse information about the computer skills, Dashboard understanding | Create |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0.5 |  |  | 2022-02-11 | 2022-02-11
BC | 55.3 | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Document the learning | Pack and Publish |  | R |  |  |  | A | 2022-02-07 | 2022-02-11 | 4 | 0.25 |  |  | 2022-02-11 | 2022-02-11
BD | 56.1 | Listing of 6 OHT VPs Preferred learning style | Eliciate the preferred way of learning a new concept from VP | Research |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BD | 56.2 | Listing of 6 OHT VPs Preferred learning style | identify the way of learning | Create |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BD | 56.3 | Listing of 6 OHT VPs Preferred learning style | Pack and publish preferred way of learning | Pack and Publish |  |  | R | A |  |  | 2022-02-07 | 2022-02-11 | 4 | 0
BE | 57.1 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Eliciate the preferred way of implement a new concept from VP | Research |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0
BE | 57.2 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Identify the way of implementation | Pack and Publish |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0
BE | 57.3 | Listing of 6 OHT VPs Preferred ways to implement new concepts | Share it with a team | Pack and ublish |  |  |  |  | R | A | 2022-02-07 | 2022-02-11 | 4 | 0
BF | 58.1 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Research about the Data lakes, Data Marts, Data Warehouse, including SWOT | Research |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 1.5 |  |  | 2022-02-10 | 2022-02-10
BF | 58.2 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Create about the Data lakes, Data Marts, Data Warehouse, including SWOT | Create |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 4 |  |  | 2022-02-10 | 2022-02-10
BF | 58.3 | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Pack and Publish the writtern briefing about Data lakes, Data Marts, Data Warehouse, including SWOT | Pack and publish |  |  | R |  |  | A | 2022-02-03 | 2022-02-06 | 3 | 1 |  |  | 2022-02-10 | 2022-02-10
BG | 59.1 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Research about the ERP, TPS and Query tools with SWOT | Research |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 1
BG | 59.2 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Create about the ERP, TPS and Query tools with SWOT | Create |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 1.8333
BG | 59.3 | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Pack and Publish the wirtten briefing about ERP, TPS and Query tools with SWOT | Pack and Publish |  |  |  | R | A |  | 2022-02-03 | 2022-02-06 | 3 | 0.83333
BH | 60.1 | VP's Written Briefing on Executive and Analytical Dashboards | Reserach about the analytical dashboard and Executive dashboard | Research | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 1 |  |  | 2022-02-07 | 2022-02-07
BH | 60.2 | VP's Written Briefing on Executive and Analytical Dashboards | Create a report explaning analytical dashboard and Executive dashboard | Create | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 0.5 |  |  | 2022-02-07 | 2022-02-07
BH | 60.3 | VP's Written Briefing on Executive and Analytical Dashboards | Pack and Publish the Report | Pack and publish | R | A |  |  |  |  | 2022-02-03 | 2022-02-06 | 3 | 0.16667 |  |  | 2022-02-07 | 2022-02-07
BI | 61.1 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 0.16667 |  |  | 2022-02-10 | 2022-02-10
BI | 61.2 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 0.66667 |  |  | 2022-02-10 | 2022-02-10
BI | 61.3 | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Pack and Publish |  | R |  |  |  | A | 2022-02-06 | 2022-02-10 | 4 | 1.1667 |  |  | 2022-02-10 | 2022-02-10
BJ | 62.1 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.25
BJ | 62.2 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5
BJ | 62.3 | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Pack and Publish | R |  |  | A |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.63333
BK | 63.1 | suggested VP training plans | Research about the Training plan | Research | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0.66667 |  |  | 2022-02-11 | 2022-02-11
BK | 63.2 | suggested VP training plans | Create a Training plan | Create | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0.25 |  |  | 2022-02-11 | 2022-02-11
BK | 63.3 | suggested VP training plans | Execute the training plan | Execute | R |  |  |  | A |  | 2022-02-11 | 2022-02-15 | 4 | 0.25 |  |  | 2022-02-11 | 2022-02-11
BL | 64.1 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 1 |  |  | 2022-02-14 | 2022-02-14
BL | 64.2 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 5.5 |  |  | 2022-02-15 | 2022-02-15
BL | 64.3 | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  |  |  | A |  | R | 2022-02-06 | 2022-02-10 | 4 | 5.5 |  |  | 2022-02-15 | 2022-02-15
BM | 65.1 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.66667
BM | 65.2 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5
BM | 65.3 | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  |  | A | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.41667
BN | 66.1 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10
BN | 66.2 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 1 |  |  | 2022-02-10 | 2022-02-10
BN | 66.3 | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.5 |  |  | 2022-02-10 | 2022-02-10
BO | 67.1 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Research and Plan about the implementation plan | Research | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.33333
BO | 67.2 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Create a implementation plan | Create | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.41667
BO | 67.3 | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Execute the implementation plan | Execute | A |  |  | R |  |  | 2022-02-06 | 2022-02-10 | 4 | 0.43333
BP | 68.1 | General configuration of Executive Dashboard using PowerBI | Research about the General configuration of Executive Dashboard using PowerBI | Research |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.1667 |  |  | 2022-02-17 | 2022-02-17
BP | 68.2 | General configuration of Executive Dashboard using PowerBI | Create about the General configuration of Executive Dashboard using PowerBI | Create |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.3333 |  |  | 2022-02-17 | 2022-02-17
BP | 68.3 | General configuration of Executive Dashboard using PowerBI | Pack and Publish General configuration of Executive Dashboard using PowerBI | Pack and Publish |  | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.91667 |  |  | 2022-02-17 | 2022-02-17
BQ | 69.1 | Executive Dashboard Metric 1 using TrackR Data Generator Data | Research about the Metric 1 | Research | R | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.75 |  |  | 2022-02-14 | 2022-02-14
BQ | 69.2 | Executive Dashboard Metric 1 using TrackR Data Generator Data | Create a Metric 1 | Create | R | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.4167 |  |  | 2022-02-14 | 2022-02-14
BQ | 69.3 | Executive Dashboard Metric 1 using TrackR Data Generator Data | Pack and Publish Metric 1 | Pack and Publish | R | R | A |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 1.25 |  |  | 2022-02-14 | 2022-02-14
BR | 70.1 | Executive Dashboard Metric 2 using TrackR Data Generator Data | Research about the Metric 2 | Research | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-08 | 2022-02-08
BR | 70.2 | Executive Dashboard Metric 2 using TrackR Data Generator Data | Create a Metric 2 | Create | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.41667 |  |  | 2022-02-08 | 2022-02-08
BR | 70.3 | Executive Dashboard Metric 2 using TrackR Data Generator Data | Pack and Publish Metric 2 | Pack and Publish | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.75 |  |  | 2022-02-08 | 2022-02-08
BS | 71.1 | Executive Dashboard Metric 3 using TrackR Data Generator Data | Research about the Metric 3 | Research |  | R |  |  | A |  | 2022-02-05 | 2022-02-10 | 5 | 2.3333 |  |  | 2022-02-08 | 2022-02-08
BS | 71.2 | Executive Dashboard Metric 3 using TrackR Data Generator Data | Create about the Metric 3 | Create |  | R |  |  | A |  | 2022-02-05 | 2022-02-10 | 5 | 5.4167 |  |  | 2022-02-08 | 2022-02-08
BS | 71.3 | Executive Dashboard Metric 3 using TrackR Data Generator Data | Pack and Publish Metric 3 | Pack and Publish |  | R |  |  | A |  | 2022-02-05 | 2022-02-10 | 5 | 6.5833 |  |  | 2022-02-08 | 2022-02-08
BT | 72.1 | Executive Dashboard Metric 4 | Research about the Metric 4 | Research | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.25 |  |  | 2022-02-08 | 2022-02-08
BT | 72.2 | Executive Dashboard Metric 4 | Create a Metric 4 | Create | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.41667 |  |  | 2022-02-08 | 2022-02-08
BT | 72.3 | Executive Dashboard Metric 4 | Pack and Publish the metric 4 | Pack and Publish | A | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.75 |  |  | 2022-02-08 | 2022-02-08
BU | 73.1 | Executive Dashboard Metric 5 | Research about the Metric 5 | Research |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.33333 |  |  | 2022-02-08 | 2022-02-08
BU | 73.2 | Executive Dashboard Metric 5 | Create a Metric 5 | Create |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.41667 |  |  | 2022-02-08 | 2022-02-08
BU | 73.3 | Executive Dashboard Metric 5 | Pack and Publish the metric 5 | Pack and Publish |  | R |  | A |  |  | 2022-02-05 | 2022-02-10 | 5 | 0.75 |  |  | 2022-02-09 | 2022-02-09
BV | 74.1 | Executive Dashboard Metric 6 | Research about the Metric 6 | Research |  | R |  |  |  | A | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-09 | 2022-02-09
BV | 74.2 | Executive Dashboard Metric 6 | Create a Metric 6 | Create |  | R |  |  |  | A | 2022-02-05 | 2022-02-10 | 5 | 0.66667 |  |  | 2022-02-09 | 2022-02-09
BV | 74.3 | Executive Dashboard Metric 6 | Research about the Metric 6 | Pack and Publish |  | R |  |  |  | A | 2022-02-05 | 2022-02-10 | 5 | 1 |  |  | 2022-02-10 | 2022-02-10
BX | 75.1 | Merged Final Report | Create Dashboard Menu/system Map | Create | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 0
BW | 75.2 | Executive Dashboard menu / system map | Create Dashboard Menu/system Map | Pack and Publish |  |  |  | A | R |  | 2022-02-07 | 2022-02-12 | 5 | 0
BX | 76.1 | Merged Final Report | Gather all the inforamtion for Final Report | Research | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 7.5
BX | 76.2 | Merged Final Report | Create Final merged Final report | Create | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 5.5
BX | 76.3 | Merged Final Report | Edit and update all the Final Merged document | Review | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 5.5
BX | 76.4 | Merged Final Report | Pack and Publish Final Report | Pack and Publish | A | A | A |  | R |  | 2022-02-15 | 2022-02-17 | 2 | 2.5
BY | 77.1 | Powerpoint Presentation | Gather all the information for Power Persentation | Research |  | A |  | R |  |  | 2022-02-13 | 2022-02-17 | 4 | 1
BY | 77.2 | Powerpoint Presentation | Create a Power Point Presentation | Create |  | A |  | R |  |  | 2022-02-13 | 2022-02-17 | 4 | 3
BY | 77.3 | Powerpoint Presentation | Pack and Publish all the information | Pack and Publish |  | A |  | R |  |  | 2022-02-13 | 2022-02-17 | 4 | 2.15
BZ | 78.1 | Final RFI report | Gather all the information for RFI Report | Research |  | A | R |  | R |  | 2022-01-28 | 2022-02-17 | 20 | 0.5 |  |  | 2022-02-18 | 2022-02-18
BZ | 78.2 | Final RFI report | Merge all the information for RFI Report | Create |  | A | R |  | R |  | 2022-01-28 | 2022-02-17 | 20 | 4.4833 |  |  | 2022-02-18 | 2022-02-18
BZ | 78.3 | Final RFI report | Publish the RFI Report | Pack and Publish |  | A | R |  | R |  | 2022-01-28 | 2022-02-17 | 20 | 1.5 |  |  | 2022-02-18 | 2022-02-18
CA | 79.1 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Research |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 3.0833 |  |  | 2022-02-10 | 2022-02-10
CA | 79.2 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Create |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 2.8333 |  |  | 2022-02-10 | 2022-02-10
CA | 79.3 | RACI+, Documentation, Backup Sheets | Create a RACI+, Documentation and Backup Sheets | Pack and Publish |  | R |  |  | A |  | 2022-01-28 | 2022-02-18 | 21 | 4.3167 |  |  | 2022-02-10 | 2022-02-10
CB | 80.1 | Time and Effort Reporting | Create a Time and Reporting sheet | Research | R | R | R | R | R | R | 2022-01-28 | 2022-02-17 | 20 | 1 |  |  | 2022-02-18 | 2022-02-18
CB | 80.2 | Time and Effort Reporting | Create a Time and Reporting sheet | Create | R | R | R | R | R | R | 2022-01-28 | 2022-02-17 | 20 | 1 |  |  | 2022-02-18 | 2022-02-18
CB | 80.3 | Time and Effort Reporting | Create a Time and Reporting sheet | Pack and Publish | R | R | R | R | R | R | 2022-01-28 | 2022-02-17 | 20 | 1 |  |  | 2022-02-18 | 2022-02-18
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
[6 empty] | Analysis of Plan R, A, C, I's: | R | 23 | 43 | 27 | 23 | 26 | 28
[7 empty] | A | 26 | 24 | 27 | 27 | 26 | 24
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | I | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Total Efforts
Person 1 Time Tracking
RowID | Team Member | Date | TaskID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | Prajwal Nayak | 2022-01-20 | 10.1 | 13:00 | 0.5 | 14:10 | 15:45 | 1.5833 | 100%
6 | Prajwal Nayak | 2022-01-20 | 10.2 | 13:30 | 0.5 | 18:20 | 20:15 | 1.9167 | 100%
7 | Prajwal Nayak | 2022-01-28 | 25.1 | 13:30 | 2 | 20:30 | 20:45 | 0.25 | 100%
8 | Prajwal Nayak | 2022-01-28 | 25.2 | 12:15 | 0.5 | 21:25 | 22:20 | 0.91667 | 100%
9 | Prajwal Nayak | 2022-01-28 | 25.3 | 13:00 | 0.5 | 22:30 | 23:10 | 0.66667 | 100%
10 | Prajwal Nayak | 2022-01-28 | 79.1 | 13:30 | 0.5 | 14:40 | 15:55 | 1.25 | 100%
11 | Prajwal Nayak | 2022-01-28 | 79.2 | 13:30 | 2 | 16:15 | 17:45 | 1.5 | 100%
12 | Prajwal Nayak | 2022-01-28 | 79.3 | 12:15 | 0.5 | 18:15 | 20:05 | 1.8333 | 100%
13 | Prajwal Nayak | 2022-02-04 | 79.1 |  |  | 13:30 | 14:45 | 1.25 | 100% | Updating RACI Matrix
14 | Prajwal Nayak | 2022-02-04 | 79.2 |  |  | 14:45 | 15:30 | 0.75 | 100% | Updating RACI Matrix
15 | Prajwal Nayak | 2022-02-04 | 79.3 | 13:00 | 0.5 | 19:05 | 20:45 | 1.6667 | 100% | Updating RACI Matrix
16 | Team G | 2022-02-05 | 42.2 | 13:30 | 0.5 | 16:05 | 18:15 | 2.1667 | 100% | Team meeting for identifying 6 metrics for executive dashboard
17 | Prajwal Nayak | 2022-02-09 | 45.1 | 12:15 | 0.5 | 19:05 | 21:15 | 2.1667 | 100%
18 | Prajwal Nayak | 2022-02-09 | 45.2 | 14:00 | 1 | 21:05 | 21:45 | 0.66667 | 100%
19 | Prajwal Nayak | 2022-02-09 | 45.3 | 15:00 | 1 | 22:05 | 22:35 | 0.5 | 100%
20 | Prajwal Nayak | 2022-02-10 | 61.1 | 17:00 | 1 | 19:05 | 19:15 | 0.16667 | 100%
21 | Prajwal Nayak | 2022-02-10 | 61.2 |  |  | 19:05 | 19:45 | 0.66667 | 100%
22 | Prajwal Nayak | 2022-02-10 | 61.3 | 13:00 | 0.5 | 20:05 | 21:15 | 1.1667 | 100%
23 | Prajwal Nayak | 2022-02-11 | 29.1 | 13:30 | 0.5 | 10:05 | 10:15 | 0.16667 | 100%
24 | Prajwal Nayak | 2022-02-11 | 29.2 | 12:15 | 0.5 | 11:05 | 11:15 | 0.16667 | 100%
25 | Prajwal Nayak | 2022-02-11 | 29.3 | 14:30 | 1.1 | 11:15 | 11:55 | 0.66667 | 100%
26 | Prajwal Nayak | 2022-02-11 | 68.1 | 14:45 | 1.1 | 14:05 | 14:45 | 0.66667 | 100%
27 | Prajwal Nayak | 2022-02-11 | 68.2 | 15:00 | 1.1 | 15:05 | 15:55 | 0.83333 | 100%
28 | Prajwal Nayak | 2022-02-11 | 68.3 | 19:00 | 1.1 | 16:05 | 16:45 | 0.66667 | 100%
29 | Anusha Asokan | 2022-01-20 | 6.1 | 20:00 | 1.1 | 18:00 | 19:00 | 1 | 100% | Researched and prepared executive summary
30 | Anusha Asokan | 2022-01-21 | 6.2 | 21:00 | 1.1 | 10:00 | 10:30 | 0.5 | 100% | Repharsed few sentences and finalized the document
31 | Anusha Asokan | 2022-01-28 | 2.1 | 22:00 | 0.25 | 19:05 | 19:15 | 0.16667 | 100% | Checked and edited the document
32 | Anusha Asokan | 2022-01-28 | 2.2 |  |  | 19:15 | 19:25 | 0.16667 | 100% | Finalized the document
33 | Anusha Asokan | 2022-01-27 | 9.1 | 13:00 | 0.5 | 15:00 | 17:30 | 2.5 | 100% | Researched for content and prepared rough draft
34 | Anusha Asokan | 2022-01-28 | 9.2 | 13:30 | 0.5 | 10:00 | 11:30 | 1.5 | 100% | Prepared fnalized document
35 | Anusha Asokan | 2022-01-20 | 10.1 | 12:15 | 0.5 | 14:00 | 16:00 | 2 | 100% | Discussed with the team on questions
36 | Anusha Asokan | 2022-01-20 | 10.2 |  |  | 18:00 | 20:00 | 2 | 100% | Researched and came up with maximum questions
37 | Anusha Asokan | 2022-01-21 | 10.3 |  |  | 14:30 | 17:30 | 3 | 100% | Discussed with the team and contributed 7 questions to the team's RFI document.
38 | Anusha Asokan | 2022-02-09 | 58.1 |  |  | 18:00 | 19:30 | 1.5 | 100% | Researched on the technologies listed
39 | Anusha Asokan | 2022-02-10 | 58.2 |  |  | 7:00 | 11:00 | 4 | 100% | Prepared SWOT Analysis for the listed technologies
40 | Anusha Asokan | 2022-02-10 | 58.3 |  |  | 13:30 | 14:30 | 1 | 100% | Finalized the document
41 | Anusha Asokan | 2022-02-10 | 44.1 |  |  | 14:30 | 15:00 | 0.5 | 100% | Researched about the metric
42 | Anusha Asokan | 2022-02-10 | 44.2 |  |  | 15:00 | 15:45 | 0.75 | 100% | Prepared report
43 | Anusha Asokan | 2022-02-10 | 44.3 |  |  | 15:45 | 16:00 | 0.25 | 100% | Finalized the document
44 | Anusha Asokan | 2022-02-10 | 13.1 |  |  | 16:00 | 16:15 | 0.25 | 100% | Researched details from VP's interview and available project documents
45 | Anusha Asokan | 2022-02-10 | 13.2 |  |  | 16:15 | 17:00 | 0.75 | 100% | Prepared process flow and documented AS-IS principle
46 | Anusha Asokan | 2022-02-10 | 13.3 |  |  | 17:00 | 17:30 | 0.5 | 100% | Finalized the document
47 | Anusha Asokan | 2022-02-10 | 66.1 |  |  | 17:00 | 17:30 | 0.5 | 100% | Researched available project documents
48 | Anusha Asokan | 2022-02-10 | 66.2 |  |  | 17:30 | 18:30 | 1 | 100% | Prepared report on suggested deliverables
49 | Anusha Asokan | 2022-02-10 | 66.3 |  |  | 18:30 | 19:00 | 0.5 | 100% | Finalized the document
50 | Anusha Asokan | 2022-02-13 | 18.1 |  |  | 9:00 | 11:00 | 2 | 100% | Researched on the topic
51 | Anusha Asokan | 2022-02-13 | 18.2 |  |  | 12:00 | 13:00 | 1 | 100% | Prepared report on benefits
52 | Anusha Asokan | 2022-02-17 | 18.3 |  |  | 16:30 | 17:30 | 1 | 100% | Finalized the document
53 | Anusha Asokan | 2022-02-14 | 38.1 |  |  | 17:00 | 18:30 | 1.5 | 100% | Researched about agile development
54 | Anusha Asokan | 2022-02-14 | 38.2 |  |  | 18:30 | 20:30 | 2 | 100% | Developed agile methodology documentation
55 | Anusha Asokan | 2022-02-17 | 38.3 |  |  | 17:30 | 18:30 | 1 | 100% | Finalized the document
56 | Anusha Asokan | 2022-02-17 | 78.1 |  |  | 16:00 | 16:30 | 0.5 | 100% | Gathered all the RFI documents
57 | Anusha Asokan | 2022-02-17 | 78.2 |  |  | 16:00 | 16:30 | 0.5 | 100% | Check the RFI documents
58 | Anusha Asokan | 2022-02-17 | 78.3 |  |  | 16:30 | 17:00 | 0.5 | 100% | FInalized the document
59 | Anusha Asokan | 2022-02-18 | 19.1 |  |  | 13:00 | 14:00 | 1 | 100% | Created Reference list
60 | Anusha Asokan | 2022-02-18 | 19.2 |  |  | 14:00 | 15:00 | 1 | 100% | Finalized detailed refernces
61 | Jigeesha Kocher | 2022-01-27 | 4.1 |  |  | 10:00 | 10:15 | 0.25 | 100% | Created the TOC for the Project Management Document
62 | Jigeesha Kocher | 2011-01-20 | 10.1 |  |  | 14:00 | 16:00 | 2 | 100% | Created the RFI document by discussing questions with team mates
63 | Jigeesha Kocher | 2011-01-21 | 10.2 |  |  | 10:00 | 12:00 | 2 | 100% | Researched on the RFI questions to be asked
64 | Jigeesha Kocher | 2011-01-22 | 10.3 |  |  | 14:30 | 17:30 | 3 | 100% | Discussed with team members and contributed 7 questions to be asked.
65 | Jigeesha Kocher | 2011-01-23 | 11.1 |  |  | 8:00 | 9:00 | 1 | 100% | Created the document for the project scope
66 | Jigeesha Kocher | 2011-01-24 | 11.2 |  |  | 10:00 | 12:00 | 2 | 100% | Researched the content for the project scope
67 | Jigeesha Kocher | 2011-01-25 | 11.3 |  |  | 3:00 | 4:00 | 1 | 100% | Finalized the project scope
68 | Jigeesha Kocher | 2022-02-03 | 14.1 |  |  | 2:00 | 2:30 | 0.5 | 100% | Discussed To-Be persons/roles / actors and interactions of Executive Decision-Making operations
69 | Jigeesha Kocher | 2022-02-05 | 14.2 |  |  | 2:30 | 3:10 | 0.66667 | 100% | Researched thoroughly about the To-Be actors/roles/interactions to be invovled in the process
70 | Jigeesha Kocher | 2022-02-07 | 14.3 |  |  | 3:15 | 4:00 | 0.75 | 100% | Published the final To-BE roles/ actions/ interactions along with the process flow
71 | Jigeesha Kocher | 2022-02-05 | 22.1 |  |  | 19:00 | 19:25 | 0.41667 | 100% | Developed the document for the risks in the operational process and possible mitigations
72 | Jigeesha Kocher | 2022-02-07 | 22.2 |  |  | 19:30 | 20:05 | 0.58333 | 100% | Researched and analyse the risks and possible mitigations in the dashboard operational process.
73 | Jigeesha Kocher | 2022-02-09 | 22.3 |  |  | 20:10 | 20:42 | 0.53333 | 100% | Finalize the possible risks to be encountered in the process
74 | Jigeesha Kocher | 2022-01-27 | 24.1 |  |  | 1:00 | 1:20 | 0.33333 | 100% | Created the document to change the scope in the report section
75 | Jigeesha Kocher | 2022-01-27 | 24.2 |  |  | 1:25 | 1:45 | 0.33333 | 100% | Researched about the change in the scope and attache the initial in the Appendix
76 | Jigeesha Kocher | 2022-01-28 | 24.3 |  |  | 2:00 | 2:20 | 0.33333 | 100% | Finalized the changes in the scope and mentioned it in the report section.
77 | Jigeesha Kocher | 2022-02-06 | 46.1 |  |  | 20:00 | 20:40 | 0.66667 | 100% | Developed document for metric 6
78 | Jigeesha Kocher | 2022-02-08 | 46.2 |  |  | 20:45 | 21:30 | 0.75 | 100% | Analysed and identified the metric
79 | Jigeesha Kocher | 2022-02-09 | 46.3 |  |  | 21:45 | 22:30 | 0.75 | 100% | Prepared and finalizedthe metric
80 | Jigeesha Kocher | 2022-02-05 | 53.1 |  |  | 6:00 | 6:20 | 0.33333 | 100% | Gather the infromation about Monthly Finance Reports used
81 | Jigeesha Kocher | 2022-02-06 | 53.2 |  |  | 6:20 | 6:40 | 0.33333 | 100% | Document the infromation
82 | Jigeesha Kocher | 2022-02-10 | 53.3 |  |  | 6:45 | 7:15 | 0.5 | 100% | Finalized the report
83 | Jigeesha Kocher | 2022-02-03 | 59.1 |  |  | 3:00 | 4:00 | 1 | 100% | Research about the ERP, TPS and Query tools with SWOT
84 | Jigeesha Kocher | 2022-02-04 | 59.2 |  |  | 5:30 | 7:20 | 1.8333 | 100% | Create about the ERP, TPS and Query tools with SWOT
85 | Jigeesha Kocher | 2022-02-05 | 59.3 |  |  | 20:00 | 20:50 | 0.83333 | 100% | Pack and Publish the wirtten briefing about ERP, TPS and Query tools with SWOT
86 | Jigeesha Kocher | 2022-02-07 | 65.1 |  |  | 2:45 | 3:25 | 0.66667 | 100% | Research and Plan about the implementation plan
87 | Jigeesha Kocher | 2022-02-09 | 65.2 |  |  | 4:30 | 5:00 | 0.5 | 100% | Create a implementation plan
88 | Jigeesha Kocher | 2022-02-10 | 65.3 |  |  | 5:15 | 5:40 | 0.41667 | 100% | Execute the implementation plan
89 | Jigeesha Kocher | 2022-02-06 | 67.1 |  |  | 5:45 | 6:05 | 0.33333 | 100% | Research and Plan about the implementation plan
90 | Jigeesha Kocher | 2022-02-08 | 67.2 |  |  | 21:00 | 21:25 | 0.41667 | 100% | Create a implementation plan
91 | Jigeesha Kocher | 2022-02-09 | 67.3 |  |  | 22:00 | 22:26 | 0.43333 | 100% | Execute the implementation plan
92 | Jigeesha Kocher | 2022-02-10 | 74.1 |  |  | 22:30 | 22:55 | 0.41667 | 100% | Research about the Metric 6
93 | Jigeesha Kocher | 2022-02-11 | 74.2 |  |  | 23:30 | 23:45 | 0.25 | 100% | Create a Metric 6
94 | Jigeesha Kocher | 2022-02-09 | 74.3 |  |  | 12:00 | 12:35 | 0.58333 | 100% | Research about the Metric 6
95 | Jigeesha Kocher | 2022-02-13 | 77.1 |  |  | 21:00 | 22:00 | 1 | 100% | Gather all the information for Power Persentation
96 | Jigeesha Kocher | 2022-02-15 | 77.2 |  |  | 14:00 | 17:00 | 3 | 100% | Create a Power Point Presentation
97 | Jigeesha Kocher | 2022-02-17 | 77.3 |  |  | 19:00 | 20:00 | 1 | 100% | Pack and Publish all the information
98 | Prajwal Nayak | 2022-02-17 | 29.1 | 13:30 | 0.5 | 19:05 | 19:15 | 0.16667 | 100%
99 | Prajwal Nayak | 2022-02-17 | 29.2 | 12:15 | 0.5 | 19:05 | 19:45 | 0.66667 | 100%
100 | Prajwal Nayak | 2022-02-17 | 29.3 | 14:30 | 1.1 | 20:05 | 21:15 | 1.1667 | 100%
101 | Prajwal Nayak | 2022-02-17 | 40.1 |  |  | 13:30 | 14:45 | 1.25 | 100%
102 | Prajwal Nayak | 2022-02-17 | 40.2 |  |  | 14:45 | 15:30 | 0.75 | 100%
103 | Prajwal Nayak | 2022-02-17 | 40.3 |  |  | 15:45 | 16:30 | 0.75 | 100%
104 | Prajwal Nayak | 2022-02-17 | 68.1 |  |  | 21:15 | 21:45 | 0.5 | 100%
105 | Prajwal Nayak | 2022-02-17 | 68.2 |  |  | 21:45 | 22:15 | 0.5 | 100%
106 | Prajwal Nayak | 2022-02-17 | 68.3 |  |  | 22:15 | 22:30 | 0.25 | 100%
107 | Chaitanya Keesari | 2022-02-17 | 16.1 |  |  | 14:10 | 15:45 | 1.5833 | 100% | Develop Document
108 | Chaitanya Keesari | 2022-02-17 | 16.2 |  |  | 18:20 | 20:15 | 1.9167 | 100% | Analyse and collect information
109 | Chaitanya Keesari | 2022-02-17 | 16.3 |  |  | 20:30 | 20:45 | 0.25 | 100% | Finalize and publish
110 | Chaitanya Keesari | 2022-02-15 | 21.1 |  |  | 21:25 | 22:20 | 0.91667 | 100% | Develop Document
111 | Chaitanya Keesari | 2022-02-15 | 21.2 |  |  | 22:30 | 23:10 | 0.66667 | 100% | Analyse and collect information
112 | Chaitanya Keesari | 2022-02-15 | 21.3 |  |  | 14:40 | 15:55 | 1.25 | 100% | Finalize and publish
113 | Chaitanya Keesari | 2022-02-13 | 27.1 |  |  | 16:15 | 17:45 | 1.5 | 100% | Develop Use case Document
114 | Chaitanya Keesari | 2022-02-13 | 27.2 |  |  | 18:15 | 20:05 | 1.8333 | 100% | Analyse and list out relation between actors and systems
115 | Chaitanya Keesari | 2022-02-13 | 27.3 |  |  | 13:30 | 14:45 | 1.25 | 100% | Finalize and publish
116 | Chaitanya Keesari | 2022-02-10 | 33.1 |  |  | 14:45 | 15:30 | 0.75 | 100% | Create navigation guide wireframe for moving forward
117 | Chaitanya Keesari | 2022-02-10 | 33.2 |  |  | 19:05 | 20:45 | 1.6667 | 100% | Prepare layout and finalize
118 | Chaitanya Keesari | 2022-02-16 | 37.1 |  |  | 15:00 | 17:30 | 2.5 | 100% | Develop pseudocode document
119 | Chaitanya Keesari | 2022-02-16 | 37.2 |  |  | 10:00 | 11:30 | 1.5 | 100% | Analyze and collect information
120 | Chaitanya Keesari | 2022-02-16 | 37.3 |  |  | 14:00 | 16:00 | 2 | 100% | Finalize and publish
121 | Chaitanya Keesari | 2022-02-13 | 39.1 |  |  | 18:00 | 20:00 | 2 | 100% | Develop Cockburn template
122 | Chaitanya Keesari | 2022-02-13 | 39.2 |  |  | 14:30 | 17:30 | 3 | 100% | Analyze and collect information
123 | Chaitanya Keesari | 2022-02-13 | 39.3 |  |  | 18:00 | 19:30 | 1.5 | 100% | Finalize and publish
124 | Chaitanya Keesari | 2022-02-09 | 42.1 |  |  | 7:00 | 11:00 | 4 | 100% | Develop document for Metric 2
125 | Chaitanya Keesari | 2022-02-10 | 42.2 |  |  | 13:30 | 14:30 | 1 | 100% | Analyze and identify metric
126 | Chaitanya Keesari | 2022-02-10 | 42.3 |  |  | 11:15 | 11:55 | 0.66667 | 100% | Prepare and Finalize
127 | Chaitanya Keesari | 2022-02-08 | 49.1 |  |  | 14:05 | 14:45 | 0.66667 | 100% | Develop document for attitude towards change
128 | Chaitanya Keesari | 2022-02-08 | 49.2 |  |  | 15:05 | 15:55 | 0.83333 | 100% | Analyse and collect information
129 | Chaitanya Keesari | 2022-02-08 | 49.3 |  |  | 16:05 | 16:45 | 0.66667 | 100% | Finalize and Publish
130 | Chaitanya Keesari | 2022-02-08 | 52.1 |  |  | 19:05 | 19:15 | 0.16667 | 100% | Develop document
131 | Chaitanya Keesari | 2022-02-08 | 52.2 |  |  | 19:05 | 19:45 | 0.66667 | 100% | Finalize document
132 | Chaitanya Keesari | 2022-02-10 | 54.1 |  |  | 18:00 | 21:05 | 3.0833 | 100% | Gather the knowledge about the Computer Based methods of Report Circulation
133 | Chaitanya Keesari | 2022-02-10 | 54.2 |  |  | 16:00 | 16:30 | 0.5 | 100% | List the knowledge about the Computer Based methods of Report Circulation
134 | Chaitanya Keesari | 2022-02-10 | 54.3 |  |  | 16:30 | 17:00 | 0.5 | 100% | Publish the knowledge
135 | Chaitanya Keesari | 2022-02-14 | 64.1 |  |  | 17:00 | 18:00 | 1 | 100% | Research and Plan about the implementation plan
136 | Chaitanya Keesari | 2022-02-15 | 64.2 |  |  | 18:00 | 23:30 | 5.5 | 100% | Create a implementation plan
137 | Chaitanya Keesari | 2022-02-15 | 64.3 |  |  | 18:00 | 23:30 | 5.5 | 100% | Execute the implementation plan
138 | Mayurkumar Rafaliya | 2022-02-09 | 1.1 |  |  | 22:00 | 22:30 | 0.5 | 100%
139 | Mayurkumar Rafaliya | 2022-02-09 | 1.2 |  |  | 22:30 | 23:30 | 1 | 100%
140 | Mayurkumar Rafaliya | 2022-02-09 | 7.1 |  |  | 23:30 | 23:50 | 0.33333 | 100%
141 | Mayurkumar Rafaliya | 2022-02-09 | 7.2 |  |  | 23:50 | 24:00 | 0.16667 | 50%
142 | Mayurkumar Rafaliya | 2022-02-10 | 7.2 |  |  | 0:00 | 0:15 | 0.25 | 50%
143 | Mayurkumar Rafaliya | 2022-02-10 | 7.3 |  |  | 0:15 | 0:25 | 0.16667 | 100%
144 | Mayurkumar Rafaliya | 2022-02-09 | 12.1 |  |  | 13:30 | 13:40 | 0.16667 | 100%
145 | Mayurkumar Rafaliya | 2022-02-09 | 12.2 |  |  | 13:40 | 14:00 | 0.33333 | 100%
146 | Mayurkumar Rafaliya | 2022-02-09 | 12.3 |  |  | 14:00 | 14:10 | 0.16667 | 100%
147 | Mayurkumar Rafaliya | 2022-02-18 | 15.1 |  |  | 13:00 | 13:50 | 0.83333 | 100%
148 | Mayurkumar Rafaliya | 2022-02-18 | 15.2 |  |  | 13:50 | 14:00 | 0.16667 | 100%
149 | Mayurkumar Rafaliya | 2022-02-10 | 20.1 |  |  | 11:00 | 11:30 | 0.5 | 100%
150 | Mayurkumar Rafaliya | 2022-02-10 | 20.2 |  |  | 14:10 | 15:10 | 1 | 100%
151 | Mayurkumar Rafaliya | 2022-02-10 | 20.3 |  |  | 16:00 | 16:15 | 0.25 | 100%
152 | Mayurkumar Rafaliya | 2022-02-11 | 30.1 |  |  | 15:00 | 15:15 | 0.25 | 100%
153 | Mayurkumar Rafaliya | 2022-02-11 | 30.2 |  |  | 23:00 | 23:15 | 0.25 | 100%
154 | Mayurkumar Rafaliya | 2022-02-11 | 30.3 |  |  | 23:15 | 23:30 | 0.25 | 100%
155 | Mayurkumar Rafaliya | 2022-02-11 | 36.1 |  |  | 15:40 | 15:50 | 0.16667 | 100%
156 | Mayurkumar Rafaliya | 2022-02-11 | 36.2 |  |  | 15:50 | 16:00 | 0.16667 | 100%
157 | Mayurkumar Rafaliya | 2022-02-11 | 36.3 |  |  | 16:00 | 16:10 | 0.16667 | 100%
158 | Mayurkumar Rafaliya | 2022-02-09 | 41.1 |  |  | 20:00 | 21:00 | 1 | 100%
159 | Mayurkumar Rafaliya | 2022-02-09 | 41.2 |  |  | 21:00 | 22:00 | 1 | 100%
160 | Mayurkumar Rafaliya | 2022-02-10 | 41.3 |  |  | 16:10 | 16:30 | 0.33333 | 100%
161 | Mayurkumar Rafaliya | 2022-02-07 | 60.1 |  |  | 22:00 | 23:00 | 1 | 100%
162 | Mayurkumar Rafaliya | 2022-02-07 | 60.2 |  |  | 23:00 | 23:30 | 0.5 | 100%
163 | Mayurkumar Rafaliya | 2022-02-07 | 60.3 |  |  | 23:30 | 23:40 | 0.16667 | 100%
164 | Mayurkumar Rafaliya | 2022-02-11 | 63.1 |  |  | 14:00 | 14:40 | 0.66667 | 100%
165 | Mayurkumar Rafaliya | 2022-02-11 | 63.2 |  |  | 14:40 | 14:55 | 0.25 | 100%
166 | Mayurkumar Rafaliya | 2022-02-11 | 63.3 |  |  | 14:45 | 15:00 | 0.25 | 100%
167 | Mayurkumar Rafaliya | 2022-02-14 | 69.1 |  |  | 17:00 | 18:30 | 1.5 | 100%
168 | Mayurkumar Rafaliya | 2022-02-14 | 69.2 |  |  | 18:30 | 19:30 | 1 | 100%
169 | Mayurkumar Rafaliya | 2022-02-14 | 69.3 |  |  | 19:30 | 20:00 | 0.5 | 100%
170 | Mayurkumar Rafaliya | 2022-02-18 | 62.1 |  |  | 14:00 | 14:15 | 0.25 | 100%
171 | Mayurkumar Rafaliya | 2022-02-18 | 62.2 |  |  | 14:15 | 14:45 | 0.5 | 100%
172 | Mayurkumar Rafaliya | 2022-02-18 | 62.3 |  |  | 14:15 | 14:53 | 0.63333 | 100%
173 | Cathleen Mathew Mundat | 2022-01-20 | 17.2 | 13:00 | 0.5 | 14:30 | 15:45 | 1.25 | 100%
174 | Cathleen Mathew Mundat | 2022-01-21 | 17.1 | 13:30 | 0.5 | 14:30 | 15:45 | 1.25 | 100%
175 | Cathleen Mathew Mundat | 2022-01-22 | 17.3 | 13:30 | 2 | 19:00 | 20:00 | 1 | 100%
176 | Cathleen Mathew Mundat | 2022-01-27 | 25.2 | 12:15 | 0.5 | 15:00 | 16:00 | 1 | 100%
177 | Cathleen Mathew Mundat | 2022-01-28 | 25.1 | 13:00 | 0.5 | 17:00 | 23:30 | 6.5 | 100%
178 | Cathleen Mathew Mundat | 2022-01-28 | 25.3 | 13:30 | 0.5 | 21:00 | 23:30 | 2.5 | 100%
179 | Cathleen Mathew Mundat | 2022-02-04 | 43.2 |  |  | 14:30 | 15:45 | 1.25 | 100%
180 | Cathleen Mathew Mundat | 2022-02-04 | 43.1 |  |  | 14:30 | 15:45 | 1.25 | 100%
181 | Cathleen Mathew Mundat | 2022-02-04 | 43.3 |  |  | 14:30 | 15:45 | 1.25 | 100%
182 | Cathleen Mathew Mundat | 2022-02-05 | 71.1 |  |  | 16:00 | 18:00 | 2 | 100%
183 | Cathleen Mathew Mundat | 2022-02-08 | 71.2 |  |  | 13:00 | 15:30 | 2.5 | 100%
184 | Cathleen Mathew Mundat | 2022-02-09 | 71.2 |  |  | 13:00 | 15:30 | 2.5 | 100%
185 | Cathleen Mathew Mundat | 2022-02-10 | 71.3 |  |  | 13:00 | 15:45 | 2.75 | 100%
186 | Cathleen Mathew Mundat | 2022-02-10 | 71.3 |  |  | 18:00 | 21:05 | 3.0833 | 100%
187 | Cathleen Mathew Mundat | 2022-02-11 | 5.1 |  |  | 16:00 | 16:30 | 0.5 | 100%
188 | Cathleen Mathew Mundat | 2022-02-11 | 5.2 |  |  | 16:30 | 17:00 | 0.5 | 100%
189 | Cathleen Mathew Mundat | 2022-02-11 | 5.3 |  |  | 17:00 | 18:00 | 1 | 100%
190 | Cathleen Mathew Mundat | 2022-02-11 | 35.1 |  |  | 18:00 | 23:30 | 5.5 | 100%
191 | Cathleen Mathew Mundat | 2022-02-11 | 35.2 |  |  | 18:00 | 23:30 | 5.5 | 100%
192 | Cathleen Mathew Mundat | 2022-02-11 | 76.1 |  |  | 16:00 | 23:30 | 7.5 | 100%
193 | Cathleen Mathew Mundat | 2022-02-11 | 76.2 |  |  | 18:00 | 23:30 | 5.5 | 100%
194 | Cathleen Mathew Mundat | 2022-02-11 | 76.3 |  |  | 18:00 | 23:30 | 5.5 | 100%
195 | Cathleen Mathew Mundat | 2022-02-17 | 28.2 |  |  | 13:30 | 14:00 | 0.5 | 100%
196 | Cathleen Mathew Mundat | 2022-02-17 | 28.1 |  |  | 14:00 | 15:00 | 1 | 100%
197 | Cathleen Mathew Mundat | 2022-02-17 | 28.3 |  |  | 14:00 | 15:00 | 1 | 100%
198 | Cathleen Mathew Mundat | 2022-02-17 | 80.1 |  |  | 15:00 | 16:00 | 1 | 100%
199 | Cathleen Mathew Mundat | 2022-02-17 | 80.2 |  |  | 14:00 | 15:00 | 1 | 100%
200 | Cathleen Mathew Mundat | 2022-02-17 | 80.3 |  |  | 14:00 | 15:00 | 1 | 100%
201 | Prajwal Nayak | 2022-02-18 | 31.1 |  |  | 10:00 | 10:15 | 0.25 | 100%
202 | Prajwal Nayak | 2022-02-18 | 31.2 |  |  | 10:15 | 10:30 | 0.25 | 100%
203 | Prajwal Nayak | 2022-02-07 | 69.1 |  |  | 18:15 | 18:30 | 0.25 | 100%
204 | Prajwal Nayak | 2022-02-07 | 69.2 |  |  | 18:30 | 18:55 | 0.41667 | 100%
205 | Prajwal Nayak | 2022-02-07 | 69.3 |  |  | 19:15 | 20:00 | 0.75 | 100%
206 | Prajwal Nayak | 2022-02-08 | 70.1 |  |  | 18:15 | 18:30 | 0.25 | 100%
207 | Prajwal Nayak | 2022-02-08 | 70.2 |  |  | 18:30 | 18:55 | 0.41667 | 100%
208 | Prajwal Nayak | 2022-02-08 | 70.3 |  |  | 19:15 | 20:00 | 0.75 | 100%
209 | Prajwal Nayak | 2022-02-08 | 71.1 |  |  | 20:10 | 20:30 | 0.33333 | 100%
210 | Prajwal Nayak | 2022-02-08 | 71.2 |  |  | 20:35 | 21:00 | 0.41667 | 100%
211 | Prajwal Nayak | 2022-02-08 | 71.3 |  |  | 21:15 | 22:00 | 0.75 | 100%
212 | Prajwal Nayak | 2022-02-09 | 72.1 |  |  | 18:15 | 18:30 | 0.25 | 100%
213 | Prajwal Nayak | 2022-02-09 | 72.2 |  |  | 18:30 | 18:55 | 0.41667 | 100%
214 | Prajwal Nayak | 2022-02-09 | 72.3 |  |  | 19:15 | 20:00 | 0.75 | 100%
215 | Prajwal Nayak | 2022-02-09 | 73.1 |  |  | 20:10 | 20:30 | 0.33333 | 100%
216 | Prajwal Nayak | 2022-02-09 | 73.2 |  |  | 20:35 | 21:00 | 0.41667 | 100%
217 | Prajwal Nayak | 2022-02-09 | 73.3 |  |  | 21:15 | 22:00 | 0.75 | 100%
218 | Prajwal Nayak | 2022-02-10 | 74.1 |  |  | 22:15 | 22:30 | 0.25 | 100%
219 | Prajwal Nayak | 2022-02-10 | 74.2 |  |  | 22:35 | 23:00 | 0.41667 | 100%
220 | Prajwal Nayak | 2022-02-10 | 74.3 |  |  | 23:05 | 23:30 | 0.41667 | 100%
221 | Prajwal Nayak | 2022-02-11 | 79.1 |  |  | 23:15 | 23:30 | 0.25 | 100%
222 | Prajwal Nayak | 2022-02-11 | 79.2 |  |  | 23:35 | 23:50 | 0.25 | 100%
223 | Prajwal Nayak | 2022-02-11 | 79.3 |  |  | 23:55 | 23:59 | 0.066667 | 100%
224 | Prajwal Nayak | 2022-02-18 | 79.1 |  |  | 14:10 | 14:30 | 0.33333 | 100%
225 | Prajwal Nayak | 2022-02-18 | 79.2 |  |  | 14:35 | 14:55 | 0.33333 | 100%
226 | Prajwal Nayak | 2022-02-18 | 79.3 |  |  | 15:15 | 16:00 | 0.75 | 100%
227 | Cathleen Mathew Mundat | 2022-02-17 | 78.2 |  |  | 20:00 | 23:59 | 3.9833 | 100%
228 | Cathleen Mathew Mundat | 2022-02-17 | 78.3 |  |  | 0:00 | 1:00 | 1 | 100%
229 | Cathleen Mathew Mundat | 2022-02-18 | 77.3 |  |  | 10:30 | 11:39 | 1.15 | 100%
230 | Cathleen Mathew Mundat | 2022-02-18 | 28.3 |  |  | 10:30 | 11:39 | 1.15 | 100%
231 | Cathleen Mathew Mundat | 2022-02-18 | 76.4 |  |  | 13:30 | 16:00 | 2.5 | 100%
232 | Prajwal Nayak | 2022-01-27 | 3.1 |  |  | 14:10 | 15:45 | 1.5833 | 100%
233 | Prajwal Nayak | 2022-01-27 | 3.2 |  |  | 18:20 | 20:15 | 1.9167 | 100%
234 | Prajwal Nayak | 2022-01-27 | 8.1 |  |  | 20:30 | 20:45 | 0.25 | 100%
235 | Prajwal Nayak | 2022-01-27 | 8.2 |  |  | 21:25 | 22:20 | 0.91667 | 100%
236 | Prajwal Nayak | 2022-01-27 | 23.1 |  |  | 22:30 | 23:10 | 0.66667 | 100%
237 | Prajwal Nayak | 2022-01-27 | 23.2 |  |  | 23:10 | 23:40 | 0.5 | 100%
238 | Prajwal Nayak | 2022-02-08 | 32.1 |  |  | 22:15 | 22:30 | 0.25 | 100%
239 | Prajwal Nayak | 2022-02-08 | 32.2 |  |  | 22:15 | 22:30 | 0.25 | 100%
240 | Prajwal Nayak | 2022-02-11 | 47.1 |  |  | 20:30 | 20:45 | 0.25 | 100%
241 | Prajwal Nayak | 2022-02-11 | 47.2 |  |  | 21:25 | 22:20 | 0.91667 | 100%
242 | Prajwal Nayak | 2022-02-11 | 55.1 |  |  | 22:30 | 23:10 | 0.66667 | 100%
243 | Prajwal Nayak | 2022-02-11 | 55.2 |  |  | 23:10 | 23:40 | 0.5 | 100%
244 | Prajwal Nayak | 2022-02-11 | 55.3 |  |  | 20:30 | 20:45 | 0.25 | 100%
245 | [5 empty] | 19:30 | 20:00 | 0.5 | 100%
246 | [5 empty] | 19:30 | 20:00 | 0.5 | 100%
247 | [5 empty] | 19:30 | 20:00 | 0.5 | 100%
248 | [5 empty] | 19:30 | 20:00 | 0.5 | 100%

## PRAJWAL
Prajwal's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | 2022-01-20 | 10.1 | 13:00 | 0.5 | 14:10 | 15:45 | 1.5833 | 100%
6 | 2022-01-20 | 10.2 | 13:30 | 0.5 | 18:20 | 20:15 | 1.9167 | 100%
7 | 2022-01-28 | 25.1 | 13:30 | 2 | 20:30 | 20:45 | 0.25 | 100%
8 | 2022-01-28 | 25.2 | 12:15 | 0.5 | 21:25 | 22:20 | 0.91667 | 100%
| 2022-01-28 | 25.3 | 13:00 | 0.5 | 22:30 | 23:10 | 0.66667 | 100%
10 | 2022-01-28 | 79.1 | 13:30 | 0.5 | 14:40 | 15:55 | 1.25 | 100%
11 | 2022-01-28 | 79.2 | 13:30 | 2 | 16:15 | 17:45 | 1.5 | 100%
12 | 2022-01-28 | 79.3 | 12:15 | 0.5 | 18:15 | 20:05 | 1.8333 | 100%
13 | 2022-02-04 | 79.1 |  |  | 13:30 | 14:45 | 1.25 | 100%
14 | 2022-02-04 | 79.2 |  |  | 14:45 | 15:30 | 0.75 | 100%
15 | 2022-02-04 | 79.3 | 13:00 | 0.5 | 19:05 | 20:45 | 1.6667 | 100%
16 | 2022-02-09 | 45.1 | 12:15 | 0.5 | 19:05 | 21:15 | 2.1667 | 100%
17 | 2022-02-09 | 45.2 | 14:00 | 1 | 21:05 | 21:45 | 0.66667 | 100%
18 | 2022-02-09 | 45.3 | 15:00 | 1 | 22:05 | 22:35 | 0.5 | 100%
19 | 2022-02-10 | 61.1 | 17:00 | 1 | 19:05 | 19:15 | 0.16667 | 100%
20 | 2022-02-10 | 61.2 |  |  | 19:05 | 19:45 | 0.66667 | 100%
21 | 2022-02-10 | 61.3 | 13:00 | 0.5 | 20:05 | 21:15 | 1.1667 | 100%
22 | 2022-02-11 | 29.1 | 13:30 | 0.5 | 10:05 | 10:15 |  | 100%
23 | 2022-02-11 | 29.2 | 12:15 | 0.5 | 11:05 | 11:15 | 0.16667 | 100%
24 | 2022-02-11 | 29.3 | 14:30 | 1.1 | 11:15 | 11:55 | 0.66667 | 100%
25 | 2022-02-11 | 68.1 | 14:45 | 1.1 | 14:05 | 14:45 | 0.66667 | 100%
26 | 2022-02-11 | 68.2 | 15:00 | 1.1 | 15:05 | 15:55 | 0.83333 | 100%
27 | 2022-02-11 | 68.3 | 19:00 | 1.1 | 16:05 | 16:45 | 0.66667 | 100%
28 | 2022-02-17 | 29.1 | 13:30 | 0.5 | 19:05 | 19:15 | 0.16667 | 100%
29 | 2022-02-17 | 29.2 | 12:15 | 0.5 | 19:05 | 19:45 | 0.66667 | 100%
30 | 2022-02-17 | 29.3 | 14:30 | 1.1 | 20:05 | 21:15 | 1.1667 | 100%
31 | 2022-02-17 | 40.1 |  |  | 13:30 | 14:45 | 1.25 | 100%
32 | 2022-02-17 | 40.2 |  |  | 14:45 | 15:30 | 0.75 | 100%
33 | 2022-02-17 | 40.3 |  |  | 15:45 | 16:30 | 0.75 | 100%
34 | 2022-02-17 | 68.1 |  |  | 21:15 | 21:45 | 0.5 | 100%
35 | 2022-02-17 | 68.2 |  |  | 21:45 | 22:15 | 0.5 | 100%
36 | 2022-02-17 | 68.3 |  |  | 22:15 | 22:30 | 0.25 | 100%
37 | 2022-02-18 | 31.1 |  |  | 10:00 | 10:15 | 0.25 | 100%
38 | 2022-02-18 | 31.2 |  |  | 10:15 | 10:30 | 0.25 | 100%
39 | 2022-02-07 | 69.1 |  |  | 18:15 | 18:30 | 0.25 | 100%
40 | 2022-02-07 | 69.2 |  |  | 18:30 | 18:55 | 0.41667 | 100%
41 | 2022-02-07 | 69.3 |  |  | 19:15 | 20:00 | 0.75 | 100%
42 | 2022-02-08 | 70.1 |  |  | 18:15 | 18:30 | 0.25 | 100%
43 | 2022-02-08 | 70.2 |  |  | 18:30 | 18:55 | 0.41667 | 100%
44 | 2022-02-08 | 70.3 |  |  | 19:15 | 20:00 | 0.75 | 100%
45 | 2022-02-08 | 71.1 |  |  | 20:10 | 20:30 | 0.33333 | 100%
46 | 2022-02-08 | 71.2 |  |  | 20:35 | 21:00 | 0.41667 | 100%
47 | 2022-02-08 | 71.3 |  |  | 21:15 | 22:00 | 0.75 | 100%
48 | 2022-02-09 | 72.1 |  |  | 18:15 | 18:30 | 0.25 | 100%
49 | 2022-02-09 | 72.2 |  |  | 18:30 | 18:55 | 0.41667 | 100%
50 | 2022-02-09 | 72.3 |  |  | 19:15 | 20:00 | 0.75 | 100%
51 | 2022-02-09 | 73.1 |  |  | 20:10 | 20:30 | 0.33333 | 100%
52 | 2022-02-09 | 73.2 |  |  | 20:35 | 21:00 | 0.41667 | 100%
53 | 2022-02-09 | 73.3 |  |  | 21:15 | 22:00 | 0.75 | 100%
54 | 2022-02-10 | 74.1 |  |  | 22:15 | 22:30 | 0.25 | 100%
55 | 2022-02-10 | 74.2 |  |  | 22:35 | 23:00 | 0.41667 | 100%
56 | 2022-02-10 | 74.3 |  |  | 23:05 | 23:30 | 0.41667 | 100%
57 | 2022-02-11 | 79.1 |  |  | 23:15 | 23:30 | 0.25 | 100%
58 | 2022-02-11 | 79.2 |  |  | 23:35 | 23:50 | 0.25 | 100%
59 | 2022-02-11 | 79.3 |  |  | 23:55 | 23:59 | 0.066667 | 100%
60 | 2022-02-18 | 79.1 |  |  | 14:10 | 14:30 | 0.33333 | 100%
61 | 2022-02-18 | 79.2 |  |  | 14:35 | 14:55 | 0.33333 | 100%
62 | 2022-02-18 | 79.3 |  |  | 15:15 | 16:00 | 0.75 | 100%
63 | 2022-01-27 | 3.1 |  |  | 14:10 | 15:45 | 1.5833 | 100%
64 | 2022-01-27 | 3.2 |  |  | 18:20 | 20:15 | 1.9167 | 100%
65 | 2022-01-27 | 8.1 |  |  | 20:30 | 20:45 | 0.25 | 100%
66 | 2022-01-27 | 8.2 |  |  | 21:25 | 22:20 | 0.91667 | 100%
67 | 2022-01-27 | 23.1 |  |  | 22:30 | 23:10 | 0.66667 | 100%
68 | 2022-01-27 | 23.2 |  |  | 23:10 | 23:40 | 0.5 | 100%
69 | 2022-02-08 | 32.1 |  |  | 22:15 | 22:30 | 0.25 | 100%
70 | 2022-02-08 | 32.2 |  |  | 22:15 | 22:30 | 0.25 | 100%
71 | 2022-02-11 | 47.1 |  |  | 20:30 | 20:45 | 0.25 | 100%
72 | 2022-02-11 | 47.2 |  |  | 21:25 | 22:20 | 0.91667 | 100%
73 | 2022-02-11 | 55.1 |  |  | 22:30 | 23:10 | 0.66667 | 100%
74 | 2022-02-11 | 55.2 |  |  | 23:10 | 23:40 | 0.5 | 100%
75 | 2022-02-11 | 55.3 |  |  | 20:30 | 20:45 | 0.25 | 100%
76 |  |  |  |  | 21:25 | 22:20 | 0.91667 | 100%
Always insert blank lines above this row!

## MAYUR
MAYUR's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | 2022-02-09 | 1.1 |  |  | 22:00 | 22:30 | 0.5 | 100%
6 | 2022-02-09 | 1.2 |  |  | 22:30 | 23:30 | 1 | 100%
7 | 2022-02-09 | 7.1 |  |  | 23:30 | 23:50 | 0.33333 | 100%
8 | 2022-02-09 | 7.2 |  |  | 23:50 | 24:00 | 0.16667 | 50%
9 | 2022-02-10 | 7.2 |  |  | 0:00 | 0:15 | 0.25 | 50%
10 | 2022-02-10 | 7.3 |  |  | 0:15 | 0:25 | 0.16667 | 100%
11 | 2022-02-09 | 12.1 |  |  | 13:30 | 13:40 | 0.16667 | 100%
12 | 2022-02-09 | 12.2 |  |  | 13:40 | 14:00 | 0.33333 | 100%
13 | 2022-02-09 | 12.3 |  |  | 14:00 | 14:10 | 0.16667 | 100%
14 | 2022-02-18 | 15.1 |  |  | 13:00 | 13:50 | 0.83333 | 100%
15 | 2022-02-18 | 15.2 |  |  | 13:50 | 14:00 | 0.16667 | 100%
16 | 2022-02-10 | 20.1 |  |  | 11:00 | 11:30 | 0.5 | 100%
17 | 2022-02-10 | 20.2 |  |  | 14:10 | 15:10 | 1 | 100%
18 | 2022-02-10 | 20.3 |  |  | 16:00 | 16:15 | 0.25 | 100%
19 | 2022-02-11 | 30.1 |  |  | 15:00 | 15:15 | 0.25 | 100%
20 | 2022-02-11 | 30.2 |  |  | 23:00 | 23:15 | 0.25 | 100%
21 | 2022-02-11 | 30.3 |  |  | 23:15 | 23:30 | 0.25 | 100%
22 | 2022-02-11 | 36.1 |  |  | 15:40 | 15:50 | 0.16667 | 100%
23 | 2022-02-11 | 36.2 |  |  | 15:50 | 16:00 | 0.16667 | 100%
24 | 2022-02-11 | 36.3 |  |  | 16:00 | 16:10 | 0.16667 | 100%
25 | 2022-02-09 | 41.1 |  |  | 20:00 | 21:00 | 1 | 100%
26 | 2022-02-09 | 41.2 |  |  | 21:00 | 22:00 | 1 | 100%
27 | 2022-02-10 | 41.3 |  |  | 16:10 | 16:30 | 0.33333 | 100%
28 | 2022-02-07 | 60.1 |  |  | 22:00 | 23:00 | 1 | 100%
29 | 2022-02-07 | 60.2 |  |  | 23:00 | 23:30 | 0.5 | 100%
30 | 2022-02-07 | 60.3 |  |  | 23:30 | 23:40 | 0.16667 | 100%
31 | 2022-02-11 | 63.1 |  |  | 14:00 | 14:40 | 0.66667 | 100%
32 | 2022-02-11 | 63.2 |  |  | 14:40 | 14:55 | 0.25 | 100%
33 | 2022-02-11 | 63.3 |  |  | 14:45 | 15:00 | 0.25 | 100%
34 | 2022-02-14 | 69.1 |  |  | 17:00 | 18:30 | 1.5 | 100%
35 | 2022-02-14 | 69.2 |  |  | 18:30 | 19:30 | 1 | 100%
36 | 2022-02-14 | 69.3 |  |  | 19:30 | 20:00 | 0.5 | 100%
37 | 2022-02-18 | 62.1 |  |  | 14:00 | 14:15 | 0.25 | 100%
38 | 2022-02-18 | 62.2 |  |  | 14:15 | 14:45 | 0.5 | 100%
39 | 2022-02-18 | 62.3 |  |  | 14:15 | 14:53 | 0.63333 | 100%
Always insert blank lines above this row!

## ANUSHA
ANUSHA's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | 2022-01-20 | 6.1 |  |  | 18:00 | 19:00 | 1 | 100% | Researched and prepared executive summary
6 | 2022-01-21 | 6.2 |  |  | 10:00 | 10:30 | 0.5 | 100% | Repharsed few sentences and finalized the document
7 | 2022-01-28 | 2.1 |  |  | 19:05 | 19:15 | 0.16667 | 100% | Checked and edited the document
8 | 2022-01-28 | 2.2 |  |  | 19:15 | 19:25 | 0.16667 | 100% | Finalized the document
9 | 2022-01-27 | 9.1 |  |  | 15:00 | 17:30 | 2.5 | 100% | Researched for content and prepared rough draft
10 | 2022-01-28 | 9.2 |  |  | 10:00 | 11:30 | 1.5 | 100% | Prepared fnalized document
11 | 2022-01-20 | 10.1 |  |  | 14:00 | 16:00 | 2 | 100% | Discussed with the team on questions
12 | 2022-01-20 | 10.2 |  |  | 18:00 | 20:00 | 2 | 100% | Researched and came up with maximum questions
13 | 2022-01-21 | 10.3 |  |  | 14:30 | 17:30 | 3 | 100% | Discussed with the team and contributed 7 questions to the team's RFI document.
14 | 2022-02-09 | 58.1 |  |  | 18:00 | 19:30 | 1.5 | 100% | Researched on the technologies listed
15 | 2022-02-10 | 58.2 |  |  | 7:00 | 11:00 | 4 | 100% | Prepared SWOT Analysis for the listed technologies
16 | 2022-02-10 | 58.3 |  |  | 13:30 | 14:30 | 1 | 100% | Finalized the document
17 | 2022-02-10 | 44.1 |  |  | 14:30 | 15:00 | 0.5 | 100% | Researched about the metric
18 | 2022-02-10 | 44.2 |  |  | 15:00 | 15:45 | 0.75 | 100% | Prepared report
19 | 2022-02-10 | 44.3 |  |  | 15:45 | 16:00 | 0.25 | 100% | Finalized the document
20 | 2022-02-10 | 13.1 |  |  | 16:00 | 16:15 | 0.25 | 100% | Researched details from VP's interview and available project documents
21 | 2022-02-10 | 13.2 |  |  | 16:15 | 17:00 | 0.75 | 100% | Prepared process flow and documented AS-IS principle
22 | 2022-02-10 | 13.3 |  |  | 17:00 | 17:30 | 0.5 | 100% | Finalized the document
23 | 2022-02-10 | 66.1 |  |  | 17:00 | 17:30 | 0.5 | 100% | Researched available project documents
24 | 2022-02-10 | 66.2 |  |  | 17:30 | 18:30 | 1 | 100% | Prepared report on suggested deliverables
25 | 2022-02-10 | 66.3 |  |  | 18:30 | 19:00 | 0.5 | 100% | Finalized the document
26 | 2022-02-13 | 18.1 |  |  | 9:00 | 11:00 | 2 | 100% | Researched on the topic
27 | 2022-02-13 | 18.2 |  |  | 12:00 | 13:00 | 1 | 100% | Prepared report on benefits
28 | 2022-02-17 | 18.3 |  |  | 16:30 | 17:30 | 1 | 100% | Finalized the document
29 | 2022-02-14 | 38.1 |  |  | 17:00 | 18:30 | 1.5 | 100% | Researched about agile development
30 | 2022-02-14 | 38.2 |  |  | 18:30 | 20:30 | 2 | 100% | Developed agile methodology documentation
31 | 2022-02-17 | 38.3 |  |  | 17:30 | 18:30 | 1 | 100% | Finalized the document
32 | 2022-02-17 | 78.1 |  |  | 16:00 | 16:30 | 0.5 | 100% | Gathered all the RFI documents
33 | 2022-02-17 | 78.2 |  |  | 16:00 | 16:30 | 0.5 | 100% | Check the RFI documents
34 | 2022-02-17 | 78.3 |  |  | 16:30 | 17:00 | 0.5 | 100% | FInalized the document
35 | 2022-02-18 | 19.1 |  |  | 13:00 | 14:00 | 1 | 100% | Created Reference list
36 | 2022-02-18 | 19.2 |  |  | 14:00 | 15:00 | 1 | 100% | Finalized detailed refernces
37 | [6 empty] | 0
38 | [6 empty] | 0
Always insert blank lines above this row!

## JIGEESHA
JIGEESHA's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | 2022-01-27 | 4.1 |  |  | 10:00 | 10:15 | 0.25 | 100% | Created the TOC for the Project Management Document
6 | 2022-01-20 | 10.1 |  |  | 14:00 | 16:00 | 2 | 100% | Created the RFI document by discussing questions with team mates
7 | 2022-01-21 | 10.2 |  |  | 10:00 | 12:00 | 2 | 100% | Researched on the RFI questions to be asked
8 | 2022-01-22 | 10.3 |  |  | 14:30 | 17:30 | 3 | 100% | Discussed with team members and contributed 7 questions to be asked.
9 | 2022-01-23 | 11.1 |  |  | 8:00 | 9:00 | 1 | 100% | Created the document for the project scope
10 | 2022-01-24 | 11.2 |  |  | 10:00 | 12:00 | 2 | 100% | Researched the content for the project scope
11 | 2022-01-25 | 11.3 |  |  | 3:00 | 4:00 | 1 | 100% | Finalized the project scope
12 | 2022-02-03 | 14.1 |  |  | 2:00 | 2:30 | 0.5 | 100% | Discussed To-Be persons/roles / actors and interactions of Executive Decision-Making operations
13 | 2022-02-05 | 14.2 |  |  | 2:30 | 3:10 | 0.66667 | 100% | Researched thoroughly about the To-Be actors/roles/interactions to be invovled in the process
14 | 2022-02-07 | 14.3 |  |  | 3:15 | 4:00 | 0.75 | 100% | Published the final To-BE roles/ actions/ interactions along with the process flow
15 | 2022-02-05 | 22.1 |  |  | 19:00 | 19:25 | 0.41667 | 100% | Developed the document for the risks in the operational process and possible mitigations
16 | 2022-02-07 | 22.2 |  |  | 19:30 | 20:05 | 0.58333 | 100% | Researched and analyse the risks and possible mitigations in the dashboard operational process.
17 | 2022-02-09 | 22.3 |  |  | 20:10 | 20:42 | 0.53333 | 100% | Finalize the possible risks to be encountered in the process
18 | 2022-01-27 | 24.1 |  |  | 1:00 | 1:20 | 0.33333 | 100% | Created the document to change the scope in the report section
19 | 2022-01-27 | 24.2 |  |  | 1:25 | 1:45 | 0.33333 | 100% | Researched about the change in the scope and attache the initial in the Appendix
20 | 2022-01-28 | 24.3 |  |  | 2:00 | 2:20 | 0.33333 | 100% | Finalized the changes in the scope and mentioned it in the report section.
21 | 2022-02-06 | 46.1 |  |  | 20:00 | 20:40 | 0.66667 | 100% | Developed document for metric 6
22 | 2022-02-08 | 46.2 |  |  | 20:45 | 21:30 | 0.75 | 100% | Analysed and identified the metric
23 | 2022-02-09 | 46.3 |  |  | 21:45 | 22:30 | 0.75 | 100% | Prepared and finalizedthe metric
24 | 2022-02-05 | 53.1 |  |  | 6:00 | 6:20 | 0.33333 | 100% | Gather the infromation about Monthly Finance Reports used
25 | 2022-02-06 | 53.2 |  |  | 6:20 | 6:40 | 0.33333 | 100% | Document the infromation
26 | 2022-02-10 | 53.3 |  |  | 6:45 | 7:15 | 0.5 | 100% | Finalized the report
27 | 2022-02-03 | 59.1 |  |  | 3:00 | 4:00 | 1 | 100% | Research about the ERP, TPS and Query tools with SWOT
28 | 2022-02-04 | 59.2 |  |  | 5:30 | 7:20 | 1.8333 | 100% | Create about the ERP, TPS and Query tools with SWOT
29 | 2022-02-05 | 59.3 |  |  | 20:00 | 20:50 | 0.83333 | 100% | Pack and Publish the wirtten briefing about ERP, TPS and Query tools with SWOT
30 | 2022-02-07 | 65.1 |  |  | 2:45 | 3:25 | 0.66667 | 100% | Research and Plan about the implementation plan
31 | 2022-02-09 | 65.2 |  |  | 4:30 | 5:00 | 0.5 | 100% | Create a implementation plan
32 | 2022-02-10 | 65.3 |  |  | 5:15 | 5:40 | 0.41667 | 100% | Execute the implementation plan
33 | 2022-02-06 | 67.1 |  |  | 5:45 | 6:05 | 0.33333 | 100% | Research and Plan about the implementation plan
34 | 2022-02-08 | 67.2 |  |  | 21:00 | 21:25 | 0.41667 | 100% | Create a implementation plan
35 | 2022-02-09 | 67.3 |  |  | 22:00 | 22:26 | 0.43333 | 100% | Execute the implementation plan
36 | 2022-02-10 | 74.1 |  |  | 22:30 | 22:55 | 0.41667 | 100% | Research about the Metric 6
37 | 2022-02-11 | 74.2 |  |  | 23:30 | 23:45 | 0.25 | 100% | Create a Metric 6
38 | 2022-02-09 | 74.3 |  |  | 12:00 | 12:35 | 0.58333 | 100% | Research about the Metric 6
39 | 2022-02-13 | 77.1 |  |  | 21:00 | 22:00 | 1 | 100% | Gather all the information for Power Persentation
40 | 2022-02-15 | 77.2 |  |  | 14:00 | 17:00 | 3 | 100% | Create a Power Point Presentation
41 | 2022-02-17 | 77.3 |  |  | 19:00 | 20:00 | 1 | 100% | Pack and Publish all the information
Always insert blank lines above this row!

## CATHLEEN
CATHLEEN's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | 2022-01-20 | 17.2 | 13:00 | 0.5 | 14:30 | 15:45 | 1.25 | 100%
6 | 2022-01-21 | 17.1 | 13:30 | 0.5 | 14:30 | 15:45 | 1.25 | 100%
7 | 2022-01-22 | 17.3 | 13:30 | 2 | 19:00 | 20:00 | 1 | 100%
8 | 2022-01-27 | 25.2 | 12:15 | 0.5 | 15:00 | 16:00 | 1 | 100%
9 | 2022-01-28 | 25.1 | 13:00 | 0.5 | 17:00 | 23:30 | 6.5 | 100%
10 | 2022-01-28 | 25.3 | 13:30 | 0.5 | 21:00 | 23:30 | 2.5 | 100%
11 | 2022-02-04 | 43.2 |  |  | 14:30 | 15:45 | 1.25 | 100%
12 | 2022-02-04 | 43.1 |  |  | 14:30 | 15:45 | 1.25 | 100%
13 | 2022-02-04 | 43.3 |  |  | 14:30 | 15:45 | 1.25 | 100%
14 | 2022-02-05 | 71.1 |  |  | 16:00 | 18:00 | 2 | 100%
15 | 2022-02-08 | 71.2 |  |  | 13:00 | 15:30 | 2.5 | 100%
16 | 2022-02-09 | 71.2 |  |  | 13:00 | 15:30 | 2.5 | 100%
17 | 2022-02-10 | 71.3 |  |  | 13:00 | 15:45 | 2.75 | 100%
18 | 2022-02-10 | 71.3 |  |  | 18:00 | 21:05 | 3.0833 | 100%
19 | 2022-02-11 | 5.1 |  |  | 16:00 | 16:30 | 0.5 | 100%
20 | 2022-02-11 | 5.2 |  |  | 16:30 | 17:00 | 0.5 | 100%
21 | 2022-02-11 | 5.3 |  |  | 17:00 | 18:00 | 1 | 100%
22 | 2022-02-11 | 35.1 |  |  | 18:00 | 23:30 | 5.5 | 100%
23 | 2022-02-11 | 35.2 |  |  | 18:00 | 23:30 | 5.5 | 100%
24 | 2022-02-11 | 76.1 |  |  | 16:00 | 23:30 | 7.5 | 100%
25 | 2022-02-11 | 76.2 |  |  | 18:00 | 23:30 | 5.5 | 100%
26 | 2022-02-11 | 76.3 |  |  | 18:00 | 23:30 | 5.5 | 100%
27 | 2022-02-17 | 28.2 |  |  | 13:30 | 14:00 | 0.5 | 100%
28 | 2022-02-17 | 28.1 |  |  | 14:00 | 15:00 | 1 | 100%
29 | 2022-02-17 | 28.3 |  |  | 14:00 | 15:00 | 1 | 100%
30 | 2022-02-17 | 80.1 |  |  | 15:00 | 16:00 | 1 | 100%
31 | 2022-02-17 | 80.2 |  |  | 14:00 | 15:00 | 1 | 100%
32 | 2022-02-17 | 80.3 |  |  | 14:00 | 15:00 | 1 | 100%
33 | 2022-02-17 | 78.2 |  |  | 20:00 | 23:59 | 3.9833 | 100%
34 | 2022-02-18 | 77.3 |  |  | 10:30 | 11:39 | 1.15 | 100%
35 | 2022-02-18 | 28.3 |  |  | 10:30 | 11:39 | 1.15 | 100%
36 | 2022-02-18 | 76.4 |  |  | 13:30 | 16:00 | 2.5 | 100%
Always insert blank lines above this row!

## CHAITANYA
CHAITANYA's Time Tracking
|  |  | Plan | (hrs) | Actual |  | (hrs)
Row | Date | ActivityID | StartTime | Duration | StartTime | EndTime | Duration | Complete% | Comments
5 | 2022-02-17 | 16.1 |  |  | 14:10 | 15:45 | 1.5833 | 100% | Develop Document
6 | 2022-02-17 | 16.2 |  |  | 18:20 | 20:15 | 1.9167 | 100% | Analyse and collect information
7 | 2022-02-17 | 16.3 |  |  | 20:30 | 20:45 | 0.25 | 100% | Finalize and publish
8 | 2022-02-15 | 21.1 |  |  | 21:25 | 22:20 | 0.91667 | 100% | Develop Document
9 | 2022-02-15 | 21.2 |  |  | 22:30 | 23:10 | 0.66667 | 100% | Analyse and collect information
10 | 2022-02-15 | 21.3 |  |  | 14:40 | 15:55 | 1.25 | 100% | Finalize and publish
11 | 2022-02-13 | 27.1 |  |  | 16:15 | 17:45 | 1.5 | 100% | Develop Use case Document
12 | 2022-02-13 | 27.2 |  |  | 18:15 | 20:05 | 1.8333 | 100% | Analyse and list out relation between actors and systems
13 | 2022-02-13 | 27.3 |  |  | 13:30 | 14:45 | 1.25 | 100% | Finalize and publish
14 | 2022-02-10 | 33.1 |  |  | 14:45 | 15:30 | 0.75 | 100% | Create navigation guide wireframe for moving forward
15 | 2022-02-10 | 33.2 |  |  | 19:05 | 20:45 | 1.6667 | 100% | Prepare layout and finalize
16 | 2022-02-16 | 37.1 |  |  | 15:00 | 17:30 | 2.5 | 100% | Develop pseudocode document
17 | 2022-02-16 | 37.2 |  |  | 10:00 | 11:30 | 1.5 | 100% | Analyze and collect information
18 | 2022-02-16 | 37.3 |  |  | 14:00 | 16:00 | 2 | 100% | Finalize and publish
19 | 2022-02-13 | 39.1 |  |  | 18:00 | 20:00 | 2 | 100% | Develop Cockburn template
20 | 2022-02-13 | 39.2 |  |  | 14:30 | 17:30 | 3 | 100% | Analyze and collect information
21 | 2022-02-13 | 39.3 |  |  | 18:00 | 19:30 | 1.5 | 100% | Finalize and publish
22 | 2022-02-09 | 42.1 |  |  | 7:00 | 11:00 | 4 | 100% | Develop document for Metric 2
23 | 2022-02-10 | 42.2 |  |  | 13:30 | 14:30 | 1 | 100% | Analyze and identify metric
24 | 2022-02-10 | 42.3 |  |  | 11:15 | 11:55 | 0.66667 | 100% | Prepare and Finalize
25 | 2022-02-08 | 49.1 |  |  | 14:05 | 14:45 | 0.66667 | 100% | Develop document for attitude towards change
26 | 2022-02-08 | 49.2 |  |  | 15:05 | 15:55 | 0.83333 | 100% | Analyse and collect information
27 | 2022-02-08 | 49.3 |  |  | 16:05 | 16:45 | 0.66667 | 100% | Finalize and Publish
28 | 2022-02-08 | 52.1 |  |  | 19:05 | 19:15 | 0.16667 | 100% | Develop document
29 | 2022-02-08 | 52.2 |  |  | 19:05 | 19:45 | 0.66667 | 100% | Finalize document
30 | 2022-02-10 | 54.1 |  |  | 18:00 | 21:05 | 3.0833 | 100% | Gather the knowledge about the Computer Based methods of Report Circulation
31 | 2022-02-10 | 54.2 |  |  | 16:00 | 16:30 | 0.5 | 100% | List the knowledge about the Computer Based methods of Report Circulation
32 | 2022-02-10 | 54.3 |  |  | 16:30 | 17:00 | 0.5 | 100% | Publish the knowledge
33 | 2022-02-14 | 64.1 |  |  | 17:00 | 18:00 | 1 | 100% | Research and Plan about the implementation plan
34 | 2022-02-15 | 64.2 |  |  | 18:00 | 23:30 | 5.5 | 100% | Create a implementation plan
35 | 2022-02-15 | 64.3 |  |  | 18:00 | 23:30 | 5.5 | 100% | Execute the implementation plan
50.8333
Always insert blank lines above this row!